## Slide 1
Medco E&P Grissik | 6th Jun 2026
MEPG Integrated Planning Process Revision (4th Version)
Executive Update for SM / SVP Endorsement • Rev 3 → Rev 4
Notes: Title. This is an executive update to secure SM/SVP endorsement of Rev 4 of the MEPG Integrated Planning & Scheduling Guideline. 10-15 minutes; detail is in the appendix.

## Slide 2
Executive Summary
Rev 4 realigns Corridor planning to corporate IBP (GN-3005) and the operational framework (GN-3007), both issued after Rev 3.
Dimension | Current State (Rev 3) | Rev 4 Improvement | Business Rationale & Expected Impact
Concept & Strategy | Stand-alone guideline; predates GN-3005 & GN-3007; objectives a simple list. | Aligned & cross-referenced to GN-3005/3007, GL-001/002; scope expanded FDP→7D; new 11-objective table. | One corporately-aligned planning language; consistent decisions across horizons.
Work Process & System | Heritage RACI; vague governance; ownership unclear. | Common work process; governance forums + fixed cadence; clarified approval authorities; OPAA defined; tools/systems. | Clear ownership and cadence; faster, accountable decision-making.
Management of Plans | Thin; limited control of what enters execution. | Gate reviews (G1/G2/G3); constraints, risk, conflict & prioritization; opportunity ID (new); change control / break-in. | Protects execution from unprepared work and uncontrolled change.
Performance Assessment | Legacy / loosely-defined KPIs. | Redefined KPIs — Schedule Attainment (SF), SPI, Break-in, Deletion — plus secondary metrics. | Objective, comparable visibility of planning performance.
Continuous Improvement | Informal; not systematic. | AAR, peer review, benchmarking and feedback loops across all horizons. | Institutional learning; sustained improvement; less NPT.
Notes: Executive summary in one matrix. The core message: Rev 3 (Nov 2024) predates the two corporate documents it now must align to - GN-3005 (Jan 2025) and GN-3007 (Jan 2026). Rev 4 is alignment, not correction of neglect. Walk the five rows left to right: current state, Rev 4 improvement, business rationale/impact.

## Slide 3
Key Changes – Concept & Strategy
From a stand-alone Rev 3 guideline to one corporately-aligned planning framework built on an 11-objective foundation.
BEFORE – Rev 3 (22 Nov 2024)
Stand-alone guideline — issued before the documents it must now align to existed.
No reference to GN-3005 (corporate IBP, Jan 2025) or GN-3007 (operational, Jan 2026).
Objectives stated as a simple list — no “how” or business value attached.
Scope limited; short-term horizons under-specified.
AFTER – Rev 4 (2026)
Aligned & explicitly cross-referenced: GN-3005 (LTP/IBP), GN-3007 (operational horizons), GL-001 FDP, GL-002 ADP, MPEP, AACE RP 37R-06.
Scope expanded to the full chain — FDP, ADP, LTP (outer-years + 24M), 12M, 90D, 30D, 7D.
New Table 1: 11 integrated-planning objectives, each with Expected Behaviour (how) + Organizational Value (why).
BUSINESS VALUE
One common planning language across all horizons — objectives now drive HSE, value creation, cost & resource efficiency, execution readiness and minimized NPT, with roles and behaviours made explicit.
Notes: Concept & Strategy. Before: a stand-alone guideline with a plain objectives list. After: cross-referenced to GN-3005/3007, GL-001/002, MPEP, AACE 37R-06; scope expanded to the full FDP-to-7D chain; new 11-objective table pairing Expected Behaviour (how) with Organizational Value (why). Value: one common language.

## Slide 4
Key Changes – Planning Horizon Evolution
Rev 4 adds the missing 12-Month and 7-Day horizons and three execution gates; detail and certainty build toward execution.
BEFORE — Rev 3: 5 horizons, no 12-Month, no 7-Day, no gates
BU Life / ADP
10-Year / LTP
24-Month / Tactical
30 / 90-Day
Detailed Operational
AFTER — Rev 4: 7 horizons + 3 execution gates
FDP
Field depletion
ADP
Asset develop.
LTP
Outer-yrs + 24M
12M
Rolling screen ★
90D
Prioritized
1
Gate 1
30D
Frozen
2
Gate 2 – Freeze
7D
Weekly control
3
Gate 3
Detail, readiness & planning certainty increase toward execution →
Net-new in Rev 4: 12-Month rolling early-screening horizon • 7-Day weekly execution control • stage-gates G1 (90D, candidates), G2 (30D, plan frozen), G3 (7D, field execution authorized).
Reflects actual practice: planners confirmed they already run this LTP→12M→90D→30D→7D flow — approved Gate 1/2/3 plans are in use today (GGSDR, Suban). See Appendix F.
Full multi-horizon framework (ownership, review forums, approval, cadence): see Appendix – Figure 2.
Notes: Strongest slide. Rev 3 had 5 horizons and no gates. Rev 4 adds the 12-Month rolling screen and the 7-Day weekly control, and installs three gates: G1 at 90D (candidates), G2 at 30D (freeze), G3 at 7D (execute). Detail and certainty increase toward execution. Full framework detail is Figure 2 in the appendix.

## Slide 5
Key Changes – Work Process & Governance
One common work process, a fixed governance cadence and clarified approval authorities replace heritage RACI.
CURRENT (Rev 3)
Heritage RACI and stakeholder map.
Governance forums and cadence not defined.
Approval authorities ambiguous (legacy “Field Manager”).
REV 4
Common work process: develop → review → approve → monitor plans, iterating across every horizon (Figure 2).
Governance forums with fixed cadence (Table 2).
Approval authorities clarified per horizon (Table 1).
OPAA = Operations Planning & Activities Assurance coordinates 12M / 90D / 30D (not “P&S Team”).
Tools & systems named: IBP module in Medco BPM, SAP (cost), GPT for STPF, BPM Work Orders, MCRS.
Governance cadence & approval authority by horizon
Horizon | Cadence | Review Forum | Approval Authority
FDP | Annual | FDP/ADP kick-off & review | Sr. VP Asset
ADP | Annual | FDP/ADP kick-off & review | CEO / COO
LTP | Bi-annual | LTP kick-off & review | CEO/COO + Sr. VP Asset
12M | Quarterly | 12M Forum | VP Operations
90D | Monthly | 90D Forum – Gate 1 | VP Operations (Gate 1)
30D | Monthly | 30D Forum – Gate 2 | OIM / OM (Gate 2, Frozen)
7D | Weekly | 7D Forum – Gate 3 | Superintendent (Gate 3)
Notes: Work process & governance. Heritage RACI replaced by a common develop-review-approve-monitor process, a fixed cadence (Table 2), and clarified per-horizon approval authorities (Table 1). OPAA - Operations Planning & Activities Assurance - coordinates 12M/90D/30D; it is not the old 'P&S Team'. Named tools: IBP in Medco BPM, SAP, GPT for STPF, BPM Work Orders, MCRS.

## Slide 6
Key Changes – Management of Plans
A new ‘Managing the Plans’ spine controls constraints, risk, conflicts, change and opportunities to protect the frozen plan.
Gate Review Criteria
Defined entry tests for G1 (90D candidates), G2 (30D freeze), G3 (7D execution).
Managing Constraints
PMI six constraints — Scope, Schedule, Budget, Quality, Resources, Risk; QRA/CBR contingency.
Risk Assessment
Integrated at 30D/90D — HAZID, HAZOP, SIMOPS, SIL, PJHA; MEPG risk matrix.
Conflict Resolution & Prioritization
Ranked by HSE, asset integrity, production loss, human factors, opportunity cost.
Opportunity Identification (NEW)
Formal step to capture and mature value-adding opportunities into the plan.
Change Control / Break-in
Controlled additions & changes to the Frozen 30D plan — nothing enters uncontrolled.
Plan Administration
Documentation, data management, version control — a single source of truth.
WHY IT MATTERS
Protects execution from unprepared work and uncontrolled change.
Flow of control: screen & prioritize → Gate 1 (90D) → Gate 2 freeze (30D) → changes only via controlled Break-in → Gate 3 execute (7D).
Notes: Management of Plans - the new control spine. Gate criteria; PMI six constraints plus QRA/CBR; risk integrated at 30/90D; conflict resolution & prioritization; NEW opportunity identification; change control / break-in on the frozen 30D plan; plan administration as single source of truth. Why it matters: protects execution from unprepared work and uncontrolled change.

## Slide 7
Key Changes – Performance & Continuous Improvement
Redefined KPIs and structured learning loops make planning performance measurable and improvable.
Redefined KPIs (Rev 4)
Primary KPI | What it measures
Schedule Attainment (with SF) | Plan delivered, adjusted by Schedule Shift Factor.
SPI | Schedule Performance Indicator vs baseline.
Plan Break-in | Unplanned work forced into the frozen plan.
Plan Deletion | Committed scope removed before execution.
Secondary metrics: plan utilization, plan stability, work efficiency, disturbance / delay.
Continuous Improvement
After-Action Reviews (AAR) capture execution learning.
Planning Compliance & Peer Review across horizons.
Business Performance Review & Benchmarking.
Feedback loops return results into the relevant planning cycle (MCRS).
EXPECTED IMPACT
Objective, comparable visibility of planning performance; institutional learning that compounds over cycles and reduces non-productive time (NPT).
Notes: Performance & continuous improvement. KPIs redefined - Schedule Attainment with Schedule Shift Factor, SPI, Plan Break-in, Plan Deletion - plus secondary metrics. Learning loops: AAR, peer review, benchmarking, business performance review, feedback into the planning cycle via MCRS. Impact: measurable performance and compounding improvement, less NPT.

## Slide 8
Summary & Recommendation
Endorse the Rev 4 direction and authorize resolution of the remaining open items to issue.
What Rev 4 delivers
Aligned to corporate IBP (GN-3005) & operational framework (GN-3007).
Complete horizon set FDP→7D with the new 12M and 7D horizons.
Three execution stage-gates (G1/G2/G3) and a Frozen 30D plan.
‘Managing the Plans’ spine: constraints, risk, conflict, change, opportunity.
Redefined KPIs and continuous-improvement loops.
Open items requiring confirmation (not resolved here)
ADP approval authority — GL-002 scope text (President Director) vs summary table (CEO); Rev 4 uses CEO/COO. → Mas Fikri / Mas Robert
FDP approval authority — GL-001 scope text (Sr Manager Subsurface) vs table (Sr VP Asset); Rev 4 uses Sr. VP Asset. → Mas Fikri / Mas Robert
Legacy “Field Manager” language remains in change-control text — conflicts with GN-3007 OIM/OM authority. → Kang Oi / Mas Fikri
GN-3007 vs GN-3008 source defect — cover (4-horizon, incl. 12M) vs header (3-horizon). Source defect, not ours. → Kang Oi
THE ASK
1. Endorse the Rev 4 direction and its alignment to GN-3005 / GN-3007.
2. Authorize resolution of the four open items with the named owners above.
3. Approve the path to issue Rev 4 once those confirmations are closed.
Notes: Summary & recommendation. Recap the deliverables, then be explicit about the four open items - present them as conflicts, do NOT resolve them live. The ask: (1) endorse the Rev 4 direction, (2) authorize resolution of the open items with named owners, (3) approve the path to issue.

## Slide 9
Appendix
Supporting detail — framework figure, matrices, gate criteria, open items, source register
Notes: Appendix divider.

## Slide 10
Appendix A – Multi-Horizon Planning Framework (Figure 2)
The complete Rev 4 framework: planning focus, review forum, ownership, approval authority and cadence by horizon.
Source: MEPG Integrated Planning & Scheduling Guideline Rev 4, Figure 2 – Multi-Horizon Planning Work Process.

## Slide 11
Appendix B – Why Now: Chronology
Rev 3 was issued before the corporate documents it must now align to existed — Rev 4 closes a structural gap, not neglect.
Date | Document | Significance
22 Nov 2024 | Corridor P&S Guideline Rev 3 (v12) | Current issued baseline. Does not reference GN-3005 or GN-3007 — they did not yet exist.
14 Jan 2025 | Corporate IBP Guideline GN-3005 Rev 1 | Signed incl. SVP Corridor Asset. Rev 3 predates it by ~2 months.
Jan 2026 | Corridor Ops Procedure GN-3007 Rev 0 (IFU) | 12M / 90D / 30D / 7D operational framework. ~14 months after Rev 3.
Jul 2026 | Rev 4 rebuild in progress | Realigns Corridor planning to both corporate documents.

## Slide 12
Appendix C – Table 1: Plan Approval & Administration
Approval authority, ownership, focal point and planning administration across all eight horizon rows.
Horizon | Coverage | Plan Ownership | Approval Authority | Focal Point | Planning Admin
FDP | Field technical planning | SM Subsurface | Sr. VP Asset | per FDP guideline | per FDP guideline
ADP | Block/Asset development | Sr. VP Asset | CEO / COO | per ADP guideline | per ADP guideline
LTP (Outer Yrs) | 10-yr+ outlook | Asset Management | CEO/COO + Sr. VP Asset | Asset Management | E&P Planning
LTP (24-Month) | Major asset activities | Asset Management | CEO/COO + Sr. VP Asset | Asset Management | E&P Planning
12M | Operationally impacting | OIM/OM + owners | VP Operations | P&S Team (OPAA) | Integrated Planner
90D | Prioritized candidates | OIM/OM + Superintendent | VP Operations (Gate 1) | P&S Team (OPAA) | Functional/Asset Planner
30D | Execution commitment | OIM/OM + Superintendent | OIM/OM (Gate 2) | P&S Team (OPAA) | Functional/Asset Planner
7D / Plan Control | Weekly field execution | Superintendent/SPV | Superintendent (Gate 3) | Functional Planner | Activity/Functional Planner
Note: FDP/ADP approval authorities and legacy “Field Manager” references carry open items — see Appendix G.

## Slide 13
Appendix D – Governance Forums & Cadence (Table 2)
Fixed review cadence and gate designation by horizon — the operating rhythm of the planning system.
Horizon | Cadence | Review Forum | Gate / Purpose
FDP / ADP | Annual | FDP/ADP kick-off & review | Strategic technical & development plans
LTP | Bi-annual | LTP / UPD LTP kick-off & review | Outer-years + 24-month outlook (3 scenarios)
12M | Quarterly | 12M Forum | Rolling early screening; not committed
90D | Monthly | 90D Forum | Gate 1 – prioritized planning candidates
30D | Monthly | 30D Forum | Gate 2 – execution commitment; plan Frozen
7D | Weekly | 7D Forum | Gate 3 – authorizes weekly field execution
— | Continuous | MCRS / feedback loops | Results returned to relevant planning cycle

## Slide 14
Appendix E – Stage-Gate Review Criteria
Three gates convert a screened outlook into an authorized, frozen and executed weekly plan.
Gate 1
90-Day Forum
Purpose: select and prioritize planning candidates.
Not an execution commitment.
Tests: priority, risk & mitigation, constraints, stakeholders & resources.
Approval: VP Operations.
Gate 2
30-Day Forum
Purpose: commit to execution — plan declared FROZEN.
Tests: readiness, risk & SIMOPS, HSE & MOC, materials on/near site.
Change only via controlled Break-in thereafter.
Approval: OIM / OM.
Gate 3
7-Day Forum
Purpose: authorize weekly field execution within the frozen window.
Tests: final readiness, site coordination, SIMOPS & execution sequencing.
Approval: Superintendent.

## Slide 15
Appendix F – Gates in Practice: Field Evidence
Rev 4 documents what Corridor already runs — approved Gate 1/2/3 plans and a signed Frozen-30D DoA form are in use today (GGSDR, Suban).
Gate 1 / 90D
“90D Gate Approval June 2026” Approved Plan
Corridor Asset, period Jul–Sep 2026, Rev 0.
Executive Decision Summary + 90-day objective.
~100 activities screened, prioritized & readiness/risk-constraint reviewed.
Gate 2 / 30D
“30-Day Operations Plan” — Frozen (Approved)
Per facility: Suban 30D, GGSDR 30D Highlight.
Document status checkbox marked Frozen (Approved).
Signed DoA approval form (GGSDR June): Activity Planner, Offsite Planner, Superintendent commit to execute.
Gate 3 / 7D
“7-Day Operations Plan” + weekly forum deck
Per facility: Suban W1-W2, Integrated 7D W2-W3 (Signed), D1–D7.
Weekly forum deck (GGSD, 28 Jun 2026): break-in requests, PPM compliance, craft-utilization KPI, deferrals.
Performance executive summary & cumulative progress.
Meeting evidence (email thread 15–21 Jul 2026, planners ⇄ E&P Planning, cc OPAA): planners confirmed the LTP→12M→90D→30D→7D flow and that routine & non-routine activities follow it. Rev 4 codifies established practice rather than introducing new process.

## Slide 16
Appendix G – Open Items for Stakeholder Confirmation
Presented as conflicts with both readings — to be confirmed by owners, not resolved in this deck.
# | Item | Conflict (both readings) | Confirm with
1 | ADP approval authority | GL-002 scope text: “must be approved by Medco EP President Director” vs summary table: “CEO”. Rev 4 Table 1 uses CEO/COO. | Mas Fikri / Mas Robert
2 | FDP approval authority | GL-001 scope text: “approved by Senior Manager Subsurface” vs summary table: “Sr VP Asset”. Rev 4 uses Sr. VP Asset. | Mas Fikri / Mas Robert
3 | Legacy “Field Manager” language | Change-control body text still references “Field Manager (FM)” — conflicts with GN-3007 OIM/OM authority adopted in Rev 4. | Kang Oi / Mas Fikri
4 | GN-3007 vs GN-3008 defect | Source cover reads GN-00-3007 (4-horizon, incl. 12M); running header reads GN-00-3008 (3-horizon, drops 12M). Defect in the source. | Kang Oi
5 | Appendix C activity inclusion | May lack a 12M column although 12M is a formal Rev 4 horizon. | Mas Fikri

## Slide 17
Appendix H – Source Register
Every change in this deck is traceable to the documents below.
Reference | Role in Rev 4
P&S Guideline Rev 3 (v12), 22 Nov 2024 | Current issued baseline being revised (ID-G-BU-GG0-PRO-GN-00-0053).
P&S Guideline Rev 4 draft (v14, accepted) | The revision presented here — tracked changes accepted.
IBP Guideline GN-3005 Rev 1 (Jan 2025) | Corporate Integrated Business Planning – LTP / IBP alignment.
Corridor Ops Procedure GN-3007 Rev 0 (Jan 2026) | 12M / 90D / 30D / 7D operational planning framework.
FDP Guideline GL-001 | Field Depletion Plan — ownership & approval reference.
ADP Guideline GL-002 | Asset Development Plan — ownership & approval reference.
AACE RP 37R-06 / PMI PMBOK | Schedule levels (L1–L5); six project constraints.
Field gate artifacts + planner email thread (Jul 2026) | Approved 90D/30D/7D plans, signed Frozen-30D DoA form, weekly forum deck — evidence of current practice (Appendix F).
Brand note: colours use the deck's existing blues (004C8F / 0070C0); exact MedcoEnergi brand hex codes are unconfirmed and should be swapped in before external use.