## Dimension Structure
L1 - Integrated Planning Process Review
L2 - Dimension to Cover | L3 - Factors per Dimension | STATUS | Content | Section Referred | Proposal-to-do | Add'l improvement points
Conceptual / Strategy | Principle | EXISTS | High-level principles of Integrated Planning: a) Cross-functional, b) Combine/sequence/coordinate activities across Operational/Tactical/Strategic horizons; c) Minimize silos; d) Maximize stakeholder value. | a) Sec 1.1 Concept & Objectives (11 objectives incl. HSE, value, cost savings); b) Sec 2.1 Philosophy. | Check w/ SVP + CLTs regarding principle | Tighten objectives into a short 'why' set tied to KPIs.
| Scope | EXISTS | What/whose activities are covered, essentially a) MEPG Asset-operated PSCs, b) Exploration & Development. c) Covers: ADP, LTP, 24-Month, 30/90-Day, detailed operational plans. | Sec 1.2 Scope. | Check w/ SVP + CLTs regarding principle | -
| Operating Philosophy | EXISTS | 7 strategy statements: a) Organization, b) Goals/Objectives, c) Integrated P&S, d) Planning Integration, e) Tools/Viz/Comms, f) Continuous Improvement, g) Structured Planning Process. | a) Sec 2.2 Strategy, function-specific practices (Ops/Shutdown, Projects, Wells, Commercial). | Check w/ SVP + CLTs regarding principle | Make philosophy testable, each principle → a behaviour/check. a) TIE IN TO CORR PEGIAT VALUES
Work Process / System | Breakdown (horizons) | EXISTS | 1) Horizons: a) BU Life/ADP, b) 10-Yr/LTP c) 24-Month d) 30/90-Day; e) Plan Control (7 days). Confirm these 5 are still the breakdown; is a 7-day tier formal? (App C uses a 7-day column). | a) Sec 2.3 Work Process Figure 2 b) App C granularity row (7-day/30/90/24mo/10yr/BU Life). | Find & compare w/ latest MPEP guidelines MIGHT DIFFERS vs MEDCO | Decide if 7-day is an official horizon or just an added granularity. If yes -> FORMALIZE, If no -> then mention as remarks *could be as detailed as 7 day
| Flow | PARTIAL | 1) End-to-end flow BU → 7-day. 2) Cyclical/iterative, tied to LTP/Budget cycle. Confirm the full top-to-bottom flow is still valid. | a) Sec 2.3 narrative + Figure 2 (referenced, not fully detailed in text). | Create swim-lane flow diagram Simple table, already included in Appendix A | 1) Swimlane diagram mapping 2) Add/remove flow + stakeholders as needed
| Stakeholders (RACI) | EXISTS | Who is involved across Asset/Functional/Field, Roles defined for: a) COO, b) SVP, c) Asset Mgmt, d) Plan Owners, e) Managers, f) Installation Mgr, g) Planning Group, h) Steering Committee. | a) Sec 2.5 Roles & Responsibilities. | Find & compare w/ latest MPEP guidelines Most likely as-is Already included in APPENDIX A | Add reference to APPENDIX A to see RACI Matrix of each person in the Section 2.5
| Approvals / Roles (by horizon) | EXISTS | Approval authority per horizon: a) BU Life→COO; b) 10-Yr→COO; d) 24-Month→SVP; e) 30/90-Day→Field Mgr/Mgrs; f) Plan Control→Field Mgrs/supervisors. | Table 1 (Plan Approval & Administration); focal points & administrators per horizon. | Find & compare w/ latest MPEP guidelines Already included in APPENDIX A | Add reference to APPENDIX A to see RACI Matrix of each person in the Section 2.5
| Governance Model | EXISTS | a) Top-down + bottom-up feedback loops across horizons b) Meeting cadence governed by TORs. | Sec 3 Governance Model; Sec 3.1 Meeting TOR (App A & B). | Find & compare w/ latest MPEP guidelines most likely as-is | Map meeting cadence (who/when/inputs/outputs) in one table.
| Tools / Systems | PARTIAL | Systems referenced: a) BPM, b) SAP/Cost Centre, c) ARIS (process maps), d) MCRS, e) SharePoint, f) WDDP, g) MPEP. Confirm current tool stack. | Scattered across Sec 2.3, 5, 6; App D references BPM/PMO. | Find & compare w/ latest MPEP guidelines add/remove tools relevant to planner (AI, etc) | Consolidate a single 'tools & systems' reference; confirm what's live.
Management of Plans | Input | EXISTS | a) Acceptance/input criteria for integrating activities; b) Level-of-detail for 30/90-Day; c) the '30-day frozen' rule (issued monthly). | Sec 5.1 Acceptance/Input; Sec 5.2 30/90 Day; App D Data Input Attribute (50 fields x Op/Tac/Strat). | Find & Compare w/ Latest MPEP guidelines add/remove acceptance criteria etc | 1) Find & Compare w/ Latest MPEP guidelines Validate the 50-field App D against what planners actually wrote.
| Activity Inclusion Criteria | EXISTS — NEW L3 | THE key operational table: a) Activities enter which horizon, b )Thresholds ($, %, risk). | Sec 4 + Appendix C (full inclusion matrix by horizon & function). | Find & compare w/ latest MPEP guidelines most likely as-is | -
| Selection / Gate Review | EXISTS | 1) Objective pass/not-pass criteria for 90/30-day; 2) Gate-check content - Sufficiency-of-Info Review & - Readiness 3) 90-day & 30-day gate requirement lists. | Sec 5.3 Gate Review Criteria (90-day & 30-day requirement lists). | Find & compare w/ latest MPEP guidelines most likely as-is | Turn into a checklist/scorecard so planners can sign off.
| Prioritization | EXISTS | 1) How conflicts get prioritized per horizon a) Strategic/Tactical = NPV+risk; b) Operational = HSE, integrity, prod loss, etc | Sec 5.6 Conflict Resolution & Plan Prioritization; App E (Prioritization Matrix, Operational). | Find & compare w/ latest MPEP guidelines most likely as-is | Add prioritization for Strategical Horizon
| Opportunity Identification | TO-BUILD | Capturing/prioritizing opportunities is listed as an objective but has NO dedicated process. To improve: Define the opportunity process + step to integrate | Mentioned only in Sec 1.1 objectives; no process section. | Add new section: a) definition -> opportunity itu apa tipenya/impact by apa? - cost? - time? - scope? - quality? b) how to assess the opportunity - OPZBB? - Flow Process Improvement? c) step to integrate into existing plan - What-to do? - Where to align/approval? | TBD??
| Output / Deliverable | TO-BUILD | No exact 'deliverables per horizon' definition exists; it's implied. To improve: Define what each horizon (ADP, FDP, LTP, etc) must produce. | Implied across Sec 2.3 & Table 1; not stated explicitly. | Add new section (TBD) | Check w/ referrences & Mas Fikri regarding what to fill out
| Constraints to Manage | EXISTS | 1) Static vs dynamic constraints definition: 2) List: - Permitting/approvals, - Resources/manpower histogram, - POB/bedding, - Crew change/logistics, - Contractor capacity, - Material readiness/supply chain, - Work pack, - O&M activities. | Sec 5.4 Managing Constraints (8 named constraint areas). | Find & compare w/ latest MPEP guidelines most likely as-is | a) Create a constraint checklist per 30/90 plan with planner, purpose: quick assessment of doc. submission/checker
| Risk Assessment | EXISTS | 1) Levels: Strategic / Tactical / Operational / Contingency. 2) Tools: - HAZID, - HAZOP, - SIMOPS, - SIL, - QRA/CBR, - PJHA, - Toolbox talks; - P10/P50/P90; risk matrix. | Sec 5.5 Risk Assessment (+ App E risk matrix reference). | Find & compare w/ latest MPEP guidelines most likely as-is | a) Confirm risk matrix (App E) is attached & current; link to inclusion criteria. b) Add/remove criteria assessment as needed
| Conflict Resolution | EXISTS | 1) Levels & criteria for resolving conflicts (Strategic/Tactical NPV+risk; 2) Operational HSE/integrity/prod loss/human factors/opp cost/prep time/fatigue). | Sec 5.6 Conflict Resolution & Plan Prioritization. | Find & compare w/ latest MPEP guidelines most likely as-is | Can provide: 1) simple escalation pat on: - what to do if conflict - doesn't align with planned horizon - (opt) resolution-time
| Plan Administration | EXISTS | 1) Documentation, 2) Data/info management (storage, governance, quality, access), 3) Plan communication & visualization. | Sec 5.7 Administering the Plan (Documentation, Data Mgmt, Comms/Viz). | Find & compare w/ latest MPEP guidelines most likely as-is | Define guidelines/action to make sure: 1) Single source of truth 2) Version-control discipline.
| Change Control | EXISTS | 1) What to do when a plan changes: definition of a 'change' to the 30-day frozen plan, 2) Approval routing (Plan Owner→OIM→FM), 3) PCR process & form. | Sec: 5.8 Change Control; Appendix F (Activity Change Request Process + PCR form). | Find & compare w/ latest MPEP guidelines most likely as-is | Digitize the PCR form; add SLA/turnaround targets.
| Cost Integration | EXISTS — NEW L3 | Operating Cost Management: 1) forecasting, 2) tracking, 3) controls; links plan changes to budget/LTP/WP&B. | Sec: 8 Alignment with Operating Cost Management. | Find & compare w/ latest MPEP guidelines most likely as-is | Connect change control & cost impact explicitly through: a) Per Horizon Swimlane Diagram (check work process/system -> FLOW)
Performance Assessment | How-to's | EXISTS | 1) Debrief/AAR, 2) Planning Compliance, 3) Peer Review — the qualitative review mechanisms. | Section: 6.1 AAR (App G), 6.2 Compliance, 6.3 Peer Review. | Find & compare w/ latest MPEP guidelines most likely as-is | Standardize an AAR template & cadence (App G has one).
| Business Metrics (KPI) | EXISTS | KPIs Main: - Schedule Attainment (w/ Shift Factor), - SPI, - Plan Break-in, - Plan Deletion. Plus secondary: - Plan Utilization, - Stability, - Work Efficiency, - Disturbance/Delay. | Sec 6.5 KPI (with equations); Sec 6.4 Business Performance Review. | Find & compare w/ latest MPEP guidelines most likely as-is | Confirm KPI definitions match what's reported in MCRS; add targets.
| Benchmarking | EXISTS — NEW L3 | 1) Shutdown benchmarking: - Operational + Projects benchmarking (MPEP); May use external/industry data. | Sec 6.6 Benchmarking Strategy. | Find & compare w/ latest MPEP guidelines most likely as-is | Define what gets benchmarked, against whom, how often.
| Reporting Cadence & Ownership | PARTIAL | 1) Who reports which metric, 2) How often, to whom. | Spread across Sec 6; MCRS referenced. | Find & compare w/ latest MPEP guidelines most likely as-is | One reporting matrix: metric → owner → cadence → forum.
Continuous Improvement | Feedback Loop | EXISTS | How lessons/SIP actions/AAR/audit findings feed back into the process. | Sec 7.1 Continuous Improvement; Steering Committee accountability. | Find & compare w/ latest MPEP guidelines most likely as-is | Close the loop visibly: action register → process update → re-issue.
| Review Cadence | EXISTS | When the guideline & process maps are reviewed: guideline as-needed/Q3, process maps annually Q3, OE reviews per BU OE lead. | Sec 7.2 Reviews & Assessments (Table 2). | Find & compare w/ latest MPEP guidelines most likely as-is | Set a fixed review trigger tied to LTP cycle.
| Ownership Model | EXISTS | Who owns continuous improvement: 1) P&S Steering Committee (led by BU P&S Lead); 2) Process owner -> accountable for revisions. | Sec 7.1; Sec 2.5 Steering Committee. | Find & compare w/ latest MPEP guidelines most likely as-is | Name current committee members & meeting cadence.
| Target / Future State | EXISTS — NEW L3 | Optional: 1) Vision of Dynamic Plan Management (scenario sensitivities w/o full re-work). 2) Decide: keep as aspiration or scope out. | Sec 9 Future State — Dynamic Plan Management. | Find & compare w/ latest MPEP guidelines + add more details | Decide whether to keep, defer, or cut from the rebuilt doc.

## Document Skeleton
Section | Subsection Old | Subsection New | Current State (rev3) | Room for Improvement | To be state (rev4) | References / External | Map to Dimension Structure
0. Document Control | 0.1 Document Information | 0.1 Document Information | 1) Document identity block: Title, Doc No (ID-G-BU-GG0-PRO-GN-00-0053), Rev 3, IFU 22 Nov 2024; 2) Ownership: Originator = Medco E&P Grissik Ltd; Information Owner = Asset Management Corridor (514018); 3) Classification codes: Area (BU), Location (GN), System (00), Doc Type (PRO), Discipline (G/G0). | 1) Content is current and adequate; 2) Only needs the revision bumped to 4 and dates refreshed on issue. | 1) [KEEP] Document identity block, updated to Rev 4 with new IFU date; 2) [EDIT] Confirm the Information Owner name is still current. | 1) Internal document-control standard. | 1) L2: Front matter (not a planning dimension); 2) Note: doc-control hygiene only.
| 0.2 Revision History | 0.2 Revision History | 1) Revision sheet (Rev 1 / 2 / 3 with dates and reason for issue); 2) Detailed change log per revision; 3) Rev 3 log highlights: LRP→LTP wording, alignment to Medco implementation, appendix re-lettering (A–G). | 1) Keep the change-log discipline; 2) Rev 4 entry must clearly state this is a full rebuild per SVP direction; 3) Summarize the structural changes so reviewers see what moved. | 1) [KEEP] Revision sheet and log format; 2) [NEW] Rev 4 change description = restructure + corporate reconciliation. | 1) None (internal). | 1) L2: Front matter.
| 0.3 Approvals | 0.3 Approvals | 1) Approval matrix per revision: Prepared / Checked / Information Owner / Sr. Manager / SVP; 2) Additional approvers listed: Ronny Darma, Reza R. Hutasoit, Rosa V. Damayanti, Robert Cahyadi. | 1) Confirm approver list and titles are still valid after any reorganization. | 1) [KEEP] Approval matrix; 2) [DECIDE] Confirm current approvers with Mas Fikri before issue. | 1) None (internal). | 1) L2: Front matter.
| 0.4 Table of Contents | 0.4 Table of Contents | 1) Auto-generated Contents and Appendices list. | 1) Will need full regeneration against the new section numbering. | 1) [EDIT] Regenerate the ToC for the rev4 structure. | 1) None (internal). | 1) L2: Front matter.
1. Introduction | 1.1 Concept & Objectives | 1.1 Concept & Objectives | 1) Purpose of Integrated Planning: cross-functional process to combine, sequence and coordinate activities across Operational / Tactical / Strategic horizons; 2) Lists 11 objectives, covering: a) HSE performance; b) value creation; c) data into actionable information; d) cost savings & resource utilization; e) communication & workforce alignment. | 1) The 11 objectives are long and read as aspirational; 2) Tighten into a focused 'why' set; 3) Tie each objective to a measurable outcome / KPI so it isn't just a feel-good statement. | 1) [EDIT] Concept statement, kept but reworded & simplify 2) [EDIT] Objectives trimmed and each tied to a KPI; 3) [DECIDE] Whether to tie objectives into Corporate / PEGAT values. | 1) Latest MPEP guideline (PIC TBC); 2) Ex-OE-P&S-RP-002 (citation removed in Rev 3). | 1) L2: Conceptual / Strategy; 2) L3: Principle; 3) Improvement: tighten + tie to KPIs.
| 1.2 Scope | 1.2 Scope | 1) Applies to MEPG Asset-operated PSCs, Exploration and Development; 2) Covers the full set of plans: a) BU Life / Asset Development Plan (ADP); b) 10-Year / Long-Term Plan (LTP); c) 24-Month / Tactical Plan; d) 30/90-Day / Operational Plan; e) detailed operational-level planning per function. | 1) Confirm the scope still matches the actual Corridor org and 2) Minor changes expected only. | 1) [KEEP] Scope statement; 2) [DECIDE] Confirm function coverage is current & aligned with MPEP Guideline | 1) Latest MPEP guideline (PIC TBC). | 1) L2: Conceptual / Strategy; 2) L3: Scope.
2. Philosophy & Strategy | 2.1 Integrated Planning Philosophy | 2.1 Integrated Planning Philosophy | 1) Cross-functional planning approach; 2) Produces resourced, prioritized and approved plans and schedules across the three horizons (Sec 2.1). | 1) The philosophy is stated but not testable; 2) Each principle should map to a behaviour or check, not just a statement. | 1) [EDIT] Philosophy reworded so each principle is testable; 2) [CHECK W/ SVP] Whether to tie in to Corridor / Corporate values. | 1) Latest MPEP guideline (PIC TBC). | 1) L2: Conceptual / Strategy; 2) L3: Operating Philosophy.
| 2.2 Integrated Planning Strategy | 2.2 Integrated Planning Strategy | 1) Seven strategy statements: a) Organization; b) Goals & Objectives; c) Integrated P&S; d) Planning Integration; e) Tools / Visualization / Communication; f) Continuous Improvement; g) structured Planning Process. | 1) The seven statements are solid; 2) Each should have a named owner and evidence of how it is applied. | 1) [KEEP] The seven strategy statements; 2) [EDIT] Add a 'how this is applied' line per statement. | 1) Latest MPEP guideline (PIC TBC). | 1) L2: Conceptual / Strategy; 2) L3: Operating Philosophy.
| N/A | 2.3 Function-Specific Practices | 1) Tailored practices per function: a) Operations & Shutdown; b) Projects (MPEP, operability assurance); c) Well Operations (WDDP, early procurement); d) Commercial (sales agreements, market drivers). | 1) Confirm the function list is complete; 2) Align the Projects and Wells practices to the current MPEP. | 1) [KEEP] Function-specific practices; 2) [EDIT] Re-align Projects and Wells practices to the latest MPEP. | 1) MPEP-PM-GUI-03 (Project Planning); 2) MPEP-PD-GUI-01 (Operability Assurance). | 1) L2: Conceptual / Strategy; 2) L3: Operating Philosophy.
3. Planning System & Horizons | N/A | 3.1 Horizon Breakdown | 1) Horizons defined as: BU Life / ADP → 10-Yr / LTP → 24-Month → 30/90-Day → Plan Control (7-D); 2) Appendix C granularity row also shows a 7-day column (Sec 2.3, Fig 2, App C). | 1) Breakdown MAY DIFFER vs Medco / corporate — needs comparison; 2) Core decision: is the 7-day an official horizon or just visualization granularity? 3) This decision shapes the entire section. | 1) [DECIDE] The 7-day status: a) if YES → formalize it as a tier; b) if NO → mention as a remark ('could be detailed down to 7-day'); 2) [EDIT] Confirm the 5-tier breakdown against MPEP guideline. | 1) Latest MPEP guideline (PIC TBC); 2) AACE 37R-06 (schedule levels). | 1) L2: Work Process / System; 2) L3: Breakdown (horizons); 3) Improvement: formalize 7-day.
| N/A | 3.2 Work Process / Flow | 1) End-to-end flow, cyclical and iterative, tied to the LTP / Budget cycle; 2) Integrates Maintenance, Shutdown, Project and Early Operations; 3) Described in text plus Figure 2 (referenced, not fully detailed). | 1) Text-heavy, with no single clean flow diagram; 2) Confirm the flow direction (BU Planning → Department → Ops); 3) Confirm a bottom-up feedback loop exists, not just top-down. | 1) [NEW] One clean swim-lane flow diagram per horizon, with feedback arrows; 2) [EDIT] Confirm flow direction and hand-offs; 3) [MOVE] A simple flow table already sits in Appendix A, reference it here. | 1) Latest MPEP guideline (PIC TBC). | 1) L2: Work Process / System; 2) L3: Flow; 3) Answers Q2 (BU → Dept → Ops).
| N/A | 3.3 Tools & Systems | N/A | Systems referenced but scattered across the document: a) BPM; b) SAP / Cost Centre; c) ARIS (process maps); d) MCRS; e) SharePoint; f) WDDP; g) MPEP. 1) No consolidated tool reference exists; 2) Some reference files were removed in Rev 3; 3) Confirm which tools are actually live. | 1) [NEW] A consolidated 'Tools & Systems' subsection; 2) [EDIT] Confirm the current stack; add or remove tools relevant to planners. | 1) Internal systems list. | 1) L2: Work Process / System; 2) L3: Tools / Systems.
4. Roles, Approvals & Governance | 2.5 Roles & Responsibilities | 4.1 Roles & Responsibilities (RACI) | 1) Roles defined for: a) COO, SVP; b) Asset Management; c) Plan Owners; d) Managers (Field/Drilling/Project/Eng/Support); e) Installation Manager; f) Planning Group; g) Steering Committee (Sec 2.5). | 1) Roles are written as list, not a matrix; 2) Check whether the roles still relevant in 2026. | 1) [EDIT] Convert roles into a RACI matrix -> tied into flow diagram 2) [MOVE] Reference Appendix A for the per-person RACI tied to Section 2.5. | 1) Latest MPEP guideline (PIC TBC). | 1) L2: Work Process / System; 2) L3: Stakeholders (RACI).
| 2.4 Plan Ownership & Approval | 4.2 Plan Ownership & Approval | 1) Approval authority per horizon (Table 1): a) BU Life → COO; b) 10-Yr → COO; c) 24-Month → SVP; d) 30/90-Day → Field Mgr / Managers; e) Plan Control → Field Mgrs / supervisors. | 1) Confirm the approver titles are current; 2) Overlaps with 4.1, split cleanly (4.1 = who's involved; 4.2 = who approves). | 1) [KEEP] Approval-by-horizon table; 2) [DECIDE] Confirm approvers; 3) [MOVE] Cross-reference the Appendix A RACI. | 1) Latest MPEP guideline (PIC TBC). | 1) L2: Work Process / System; 2) L3: Approvals / Roles.
| N/A (mixed with 2.5 - Roles and Responsibility) | 4.3 Governance Model & Meeting TORs | 1) Top-down and bottom-up feedback loops across horizons; 2) Meeting cadence governed by Terms of Reference (Sec 3, 3.1; App A & B). | 1) Meeting cadence is not shown anywhere; 2) Check if the governance model still matches reality. | 1) [KEEP] Governance model; 2) [NEW] One meeting-cadence table (who / when / inputs / outputs). | 1) Latest MPEP guideline (PIC TBC). | 1) L2: Work Process / System; 2) L3: Governance Model.
5. Activity Inclusion Criteria | N/A | 5.1 Inclusion Criteria Matrix | 1) Defines which activities enter which horizon, with thresholds ($, %, risk), by function; 2) Currently sits in Sec 4 plus Appendix C; 3) Aligned to AACE schedule levels. | 1) This is the most operationally important table in the document; 2) But it floats between Input and Selection and lives in an appendix; 3) It deserves promotion to a named body section. | 1) [MOVE] Promote the inclusion matrix from appendix to a body section; 2) [EDIT] Pressure-test thresholds and $ bands with Ops / Projects. | 1) AACE 37R-06; 2) Appendix C. | 1) L2: Management of Plans; 2) L3: Activity Inclusion Criteria.
| 4. Criteria of Activities Inclusion into Plan | 5.2 Schedule Levels (AACE) | 1) Maps horizons to AACE standards levels: a) 10-Yr = Level 1; b) 24-Month = breakdown of Level 1; c) 30/90-Day = Level 3 (critical path); d) Plan Control = Levels 4 / 5 (Sec 4). | 1) Fine as-is; 2) Keep the AACE mapping explicit alongside the matrix. | 1) [KEEP] AACE level mapping. | 1) AACE International RP 37R-06. | 1) L2: Management of Plans; 2) L3: Activity Inclusion Criteria.
6. Managing the Plans | 5.1 Acceptance / Input Criteria | 6.1 Acceptance / Input Criteria | 1) Input criteria to integrate activities from various sources; 2) Consistency needed for compatibility and to surface conflicts/synergies; 3) Typical inputs per horizon detailed in Appendix D (50-field Data Input Attribute). | 1) Validate the 50-field Appendix D against what planners actually capture; 2) Trim or add fields to match practice. | 1) [KEEP] Acceptance / input criteria; 2) [EDIT] Validate the Appendix D fields with planners. | 1) Appendix D; 2) Latest MPEP guideline (PIC TBC). | 1) L2: Management of Plans; 2) L3: Input.
| 5.2 30/90-Day Plan & Frozen Window | 6.2 30/90-Day Plan & Frozen Window | 1) First 30 days of an approved plan are 'frozen' (issued monthly); 2) Required activity detail list (activity no., man-hours, dates, durations, POB, contractor readiness, etc.); 3) Jobs removed if gate requirements not met 30 days prior (Sec 5.2). | - Content wise already OK - add details list to Appendix D and to the gate checklist (6.3). | 1) [KEEP] Frozen-window rule and detail list; 2) [EDIT] Cross-link to the gates and Appendix D. | 1) Appendix D. | 1) L2: Management of Plans; 2) L3: Input.
| 5.3 Gate Review Criteria | 6.3 Gate Review (Selection) | 1) Objective pass/not-pass criteria for the 90/30-day plan; 2) Two gate reviews: a) Sufficiency-of-Info Review; b) Readiness Gate Review; 3) Explicit 90-day and 30-day gate requirement lists (Sec 5.3). | - list are ok but not intuitive - possible to turn them into a checklist / scorecard planners can sign off (pass / not-pass). | 1) [EDIT] Convert the gate lists into a sign-off checklist / scorecard; 2) [KEEP] The two-gate concept. | 1) Latest MPEP guideline (PIC TBC). | 1) L2: Management of Plans; 2) L3: Selection / Gate Review.
| 5.4 Managing Constraints | 6.4 Managing Constraints | 1) Constraints split into static vs dynamic; 2) Eight named constraint areas: a) Permitting & approvals; b) Resources & manpower histogram; c) POB & bedding capacity; d) Crew change & logistics; e) Contractor capacity; f) Material readiness & supply chain; g) Work pack; h) O&M activities (Sec 5.4). | 1) No quick tool exists for planners; 2) Add a per-plan constraint checklist for fast doc-submission / checking. | 1) [KEEP] The eight constraint areas; 2) [NEW] A constraint checklist per 30/90 plan (purpose: quick assessment for the planner/checker). | 1) Latest MPEP guideline (PIC TBC). | 1) L2: Management of Plans; 2) L3: Constraints to Manage.
| 5.5 Risk Assessment | 6.5 Risk Assessment | 1) Risk levels: Strategic / Tactical / Operational / Contingency; 2) Tools referenced: a) HAZID, HAZOP; b) SIMOPS, SIL; c) QRA / CBR; d) PJHA, toolbox talks; 3) P10 / P50 / P90; risk matrix in Appendix E (Sec 5.5). | 1) Confirm the Appendix E risk matrix is actually attached and current; 2) Explicitly link risk assessment to the inclusion criteria. | 1) [KEEP] Risk levels and tools; 2) [DECIDE] Confirm Appendix E is populated; 3) [EDIT] Link risk to inclusion criteria. | 1) Appendix E; 2) Latest MPEP guideline (PIC TBC). | 1) L2: Management of Plans; 2) L3: Risk Assessment.
| 5.6 Conflict Resolution & Prioritization | 6.6 Conflict Resolution & Prioritization | 1) Prioritization levels & criteria: a) Strategic / Tactical = NPV + risk; b) Operational = HSE, integrity, production loss, human factors, opportunity cost, prep time, fatigue; 2) Operational matrix in Appendix E; 3) Rev 3 deleted the strategic/tactical matrices (Sec 5.6). | 1) No clear escalation path when horizons disagree; 2) Strategic-horizon prioritization was removed and should return in lightweight form. | 1) [NEW] Add Strategic-Horizon prioritization; 2) [NEW] A simple escalation path: a) what to do on conflict; b) what if it doesn't align with the planned horizon; c) (optional) resolution time; 3) [KEEP] Operational criteria. | 1) Appendix E; 2) Latest MPEP guideline (PIC TBC). | 1) L2: Management of Plans; 2) L3: Conflict Resolution + Prioritization.
| N/A | 6.7 Opportunity Identification | 1) Not a process today, only named as an objective in Sec 1.1; 2) No dedicated section exists. | 1) Genuine gap; 2) Define what an opportunity is, how it's assessed, and how it enters the plan. | 1) [NEW] Definition: what an opportunity is, typed by impact: a) cost; b) time; c) scope; d) quality; 2) [NEW] How to assess it (e.g. OPZBB, process-improvement flow); 3) [NEW] Step to integrate into the existing plan — what to do, where to align / approve. | 1) Latest MPEP guideline (PIC TBC). | 1) L2: Management of Plans; 2) L3: Opportunity Identification (to-build).
| N/A | 6.8 Output / Deliverables per Horizon | 1) No crisp 'deliverable per horizon' definition; 2) It's only implied across Sec 2.3 and Table 1. | 1) Define what each horizon must produce; 2) Specify the plan format, owner, and cadence; 3) Check references and confirm with Mas Fikri what to fill. | 1) [NEW] A deliverables table per horizon (ADP / LTP / 24mo / 30-90 / 7-day), covering: a) output; b) format; c) owner; d) cadence. | 1) Latest MPEP guideline (PIC TBC); 2) Confirm with Mas Fikri. | 1) L2: Management of Plans; 2) L3: Output / Deliverable (to-build).
| N/A | 6.9 Plan Administration | 1) Documentation responsibilities per horizon; 2) Data / information management: a) storage & repository; b) governance & control; c) quality & completeness; d) user access; 3) Plan communication & visualization (Sec 5.7). | 1) Add an explicit single-source-of-truth rule; 2) Add version-control discipline. | 1) [KEEP] Admin, data and comms content; 2) [NEW] Single source of truth + version-control rule. | 1) Internal data-management procedures (IT). | 1) L2: Management of Plans; 2) L3: Plan Administration.
| N/A | 6.10 Change Control | 1) Defines a 'change' to the 30-day frozen plan (add / delay / extra budget / substantial change); 2) Approval routing: Plan Owner → OIM → Field Manager; 3) PCR process and form (Sec 5.8; Appendix F). | 1) The PCR is manual; 2) Digitize the form and add SLA / turnaround targets. | 1) [KEEP] Change definition and approval routing; 2) [NEW] Digitize the PCR; add SLA / turnaround time targets. | 1) Appendix F. | 1) L2: Management of Plans; 2) L3: Change Control.
7. Cost Integration | 8. Operating Cost Management Alignment | 7.1 Operating Cost Management Alignment | 1) Integrates cost forecasting, tracking and controls; 2) Manages acceleration / deferral / deletion / addition / cost minimization; 3) Links plan changes to budget / LTP / WP&B (Sec 8). | 1) No specific section in the rev3; 2) Connect change-control and cost impact explicitly; 3) Add a per-horizon cost swim-lane. | 1) [MOVE] Promote to its own section; 2) [NEW] Per-horizon cost swim-lane (link to 3.2 Flow); 3) [EDIT] Explicit change ↔ cost-impact link. | 1) LTP / WP&B cycle; 2) Appendix B TORs. | 1) L2: Management of Plans; 2) L3: Cost Integration (new).
8. Performance Assessment | 6.1 Debrief / AAR | 8.1 Debrief / AAR | 1) AAR purpose: learn from successes and failures, review variances from plan; 2) Benefits and process described (Sec 6.1); 3) Appendix G holds the full how-to and template. | 1) Standardize an AAR template and cadence (Appendix G already has one). | 1) [KEEP] AAR content; 2) [EDIT] Standardize the template and cadence. | 1) Appendix G. | 1) L2: Performance Assessment; 2) L3: How-to's.
| 6.2 Planning Compliance | 8.2 Planning Compliance | 1) Requires multilateral communication between planners, plan users and owners; 2) Compliance = understanding and value, not just adherence (Sec 6.2). | 1) Not connected to it to the review cadence in Section 9. | 1) [KEEP] Compliance content; 2) [EDIT] Cross-link to review cadence. | 1) None (internal). | 1) L2: Performance Assessment; 2) L3: How-to's.
| 6.3 Peer Review | 8.3 Peer Review | 1) Independent observers evaluate planned activities; 2) Criteria: a) shutdowns causing ≥50% rate reduction; b) high / significant safety-risk activities; 3) Projects covered via MPEP (Sec 6.3). | 1) Confirm the peer-review SharePoint location is current. | 1) [KEEP] Peer review content; 2) [DECIDE] Confirm locations / links to specific sharepoint. | 1) MPEP; 2) Field Ops Planning SharePoint. | 1) L2: Performance Assessment; 2) L3: How-to's.
| 6.4 Business Performance Review | 8.4 Business Performance Review | 1) Three components: a) Governance; b) Documentation; c) Metrics; 2) Metrics span milestones / production / cost (plan-on-plan, gate-on-gate, YoY) (Sec 6.4). | 1) Ensure it link directly to the KPI definitions in 8.5. | 1) [KEEP] BPR framework; 2) [EDIT] Cross-link to KPIs. | 1) None (internal). | 1) L2: Performance Assessment; 2) L3: Business Metrics.
| 6.5 KPIs | 8.5 KPIs | 1) Primary KPIs with equations: a) Schedule Attainment (with Shift Factor); b) SPI; c) Plan Break-in; d) Plan Deletion; 2) Secondary measures: Plan Utilization, Stability, Work Efficiency, Disturbance/Delay; 3) Rev 3 renamed several of these (Sec 6.5). | 1) Confirm KPI definitions match what MCRS actually reports; 2) Add a target per KPI. | 1) [KEEP] The four primary KPIs and equations; 2) [EDIT] Reconcile with MCRS; add targets. | 1) MCRS; 2) Latest MPEP guideline (PIC TBC). | 1) L2: Performance Assessment; 2) L3: Business Metrics (KPI).
| 6.6 Benchmarking | 8.6 Benchmarking | 1) Two areas: a) Shutdown benchmarking (Operational); b) Projects benchmarking (MPEP); 2) May use external / industry data (Sec 6.6). | 1) Define what gets benchmarked, against whom, and how often. | 1) [KEEP] Benchmarking strategy; 2) [EDIT] Specify scope, peers and frequency. | 1) MPEP; 2) External / industry data. | 1) L2: Performance Assessment; 2) L3: Benchmarking (new).
| N/A | 8.7 Reporting Cadence & Ownership | 1) Implied across Sec 6; MCRS referenced; 2) Not consolidated anywhere. | 1) No table talking about single reporting matrix exists; 2) Add one mapping metric → owner → cadence → forum. | 1) [NEW] A reporting matrix covering: a) metric; b) owner; c) cadence; d) forum. | 1) MCRS. | 1) L2: Performance Assessment; 2) L3: Reporting Cadence (new).
9. Continuous Improvement | 7.1 Continuous Improvement Program | 9.1 Continuous Improvement Program | 1) Structured improvement program; 2) Steering Committee accountable for the CI culture; 3) Issued through a Strategic Improvement Plan with corrective actions (Sec 7.1). | 1) Close the loop visibly: action register → process update → re-issue. | 1) [KEEP] CI program; 2) [NEW] Visible feedback loop (action register → update → re-issue). | 1) Latest MPEP guideline (PIC TBC). | 1) L2: Continuous Improvement; 2) L3: Feedback Loop.
| 7.2 Review Cadence | 9.2 Review Cadence | 1) Review schedule (Table 2): a) guideline reviewed as-needed / Q3; b) process maps annually in Q3; c) OE reviews per BU OE lead (Sec 7.2). | 1) Set a fixed review trigger tied to the LTP cycle, not just 'as needed'. | 1) [KEEP] Review table; 2) [EDIT] Fixed trigger tied to the LTP cycle. | 1) ARIS (process maps). | 1) L2: Continuous Improvement; 2) L3: Review Cadence.
| N/A | 9.3 Ownership Model | 1) P&S Steering Committee owns CI, led by the BU P&S Lead; 2) Process owner accountable for revisions (Sec 7.1; Sec 2.5). | 1) Name the current committee members and their meeting cadence. | 1) [KEEP] Ownership model; 2) [DECIDE] Confirm committee membership and the BU P&S Lead. | 1) None (internal knowledge) | 1) L2: Continuous Improvement; 2) L3: Ownership Model.
10. Future State (optional) | 9. Dynamic Plan Management | 10.1 Dynamic Plan Management | 1) Vision of decision-makers running scenario sensitivities (price / FX / inflation) without full re-work; 2) Centralized planning data aligning budget, economic and financial processes (Sec 9). | 1) Aspirational rather than operational; 2) Decide: keep as vision, defer, or cut from the rebuilt doc. | 1) [DECIDE] Keep / defer / cut; 2) [EDIT] If kept, label clearly as a target state: a) table of current, room for improvement, to-be-state | 1) Latest MPEP guideline (PIC TBC). 2) Internal discussion | 1) L2: Continuous Improvement; 2) L3: Target / Future State (new).
Appendices | Appendix A — BU Life Planning | Appendix A — BU Life Planning | 1) Four components: a) Strategy Development & Scenario Planning; b) Long-Term Growth Plan; c) LTP (10+ years); d) End-of-Life Strategy; 2) Ownership and storage table per component. | 1) Keep; 2) Becomes the reference anchor for Flow (3.2) and RACI (4.1). | 1) [KEEP] BU Life Planning; 2) [MOVE] Anchor the RACI and flow cross-references here. | 1) Confidential SharePoint / Drive. | 1) L2: Conceptual/Strategy + Work Process.
| Appendix B — Meeting TORs | Appendix B — Meeting TORs | 1) Per-horizon meeting Terms of Reference (referenced). | 1) Expand so each horizon's TOR is explicit: a) purpose; b) attendees; c) inputs; d) outputs; e) cadence. | 1) [KEEP] TORs; 2) [EDIT] Expand per-horizon detail. | 1) None (internal). | 1) L2: Work Process; 2) L3: Governance.
| Appendix C — Inclusion Criteria Matrix | Appendix C — Inclusion Criteria Matrix | 1) Full activity-inclusion matrix by horizon and function, with thresholds. | 1) Keep — now referenced from the new Section 5; 2) Pressure-test the $ bands. | 1) [KEEP] Matrix; 2) [EDIT] Validate thresholds. | 1) AACE 37R-06. | 1) L2: Management of Plans; 2) L3: Inclusion Criteria.
| Appendix D — Data Input Attributes | Appendix D — Data Input Attributes | 1) 50-field input table by horizon, with Operational / Tactical / Strategic mandatory flags. | 1) Validate with planners; 2) Trim or add fields to match actual practice. | 1) [KEEP] Attribute table; 2) [EDIT] Validate fields. | 1) None (internal). | 1) L2: Management of Plans; 2) L3: Input.
| Appendix E — Prioritization & Risk Matrix | Appendix E — Prioritization & Risk Matrix | 1) Operational prioritization matrix; 2) Risk matrix (both referenced). | 1) Confirm both are actually populated (Rev 3 removed some matrices). | 1) [DECIDE] Confirm populated; 2) [NEW] Re-add strategic prioritization if needed. | 1) None (internal). | 1) L2: Management of Plans; 2) L3: Risk + Prioritization.
| Appendix F — Change Request (PCR) | Appendix F — Change Request (PCR) | 1) PCR process (new / delete / modify); 2) PCR form template. | 1) Consider digitizing; 2) Keep the form for reference. | 1) [KEEP] PCR process and form; 2) [NEW] Add a digital-version note. | 1) None (internal). | 1) L2: Management of Plans; 2) L3: Change Control.
| Appendix G — After Action Review | Appendix G — After Action Review | 1) AAR how-to (plan / prepare / conduct / follow-up); 2) AAR template; 3) Value-of-$-save capture. | 1) Keep; 2) Promote the template into Section 8.1 by reference. | 1) [KEEP] AAR how-to and template. | 1) None (internal). | 1) L2: Performance Assessment; 2) L3: How-to's.

## LOQ
LIST OF QUESTIONS - P&S CORRIDOR:
The unknowns?
corporate PIC utk guideline terbaru? Mas Robert/Planning
| ada successor corporate utk OE-P&S-RP-002? |  | check w/ corporate guidelines
ada versi yg lebih baru utk salah satu/both document?
confirm Rev.3 -> hasil localization dr global RP OE-P&S-RP-002? (citation sengaja di-remove atau memang udah ga ada parent doc?)
clarify expectation Pak Tri:
| rewrite total? | update ke current processes di Corridor |  |  | To check:
| re-align ke corporate? | Short-term -> Fahmi/Mas Oi |  |  | - corp guidelines planning -> heritagenya OE-P&S-RP-002
| content improvement aja? | Long-term/Medium -> Mas Robert |  |  | a) Horizon
| scope/boundary sampai mana? |  | Ada references/documentation |  | b) Scope
c) Content scenario
confirm planning horizon:
7-day planning masih applicable -> formal/nggak sebetulnya?
5-tier breakdown masih dipakai? -> who to confirm
Steering Committee:
| BU P&S Lead sekarang siapa? |  |  | To validate -> masih ada apa enggak si BU P&S Lead
| committee member sekarang siapa aja? |  |  |  | apakah masih asset/plannign yg handle?
how to become one?
To ask:
Who to interview interview? validate actual process vs document? (BU Planning / Department / Ops) |  |  |  |  | Short-term -> Fahmi/Mas Oi -> intvw w/ SPV/Planner (ask evidence, comparison, etc)
a) planner to ask for whole process
align review timeline: | [5 empty] | b) mas fahmi/mas oi to confirm
milestone 2–3 minggu
| expected output utk first discussion / review meeting |  |  |  | Long-term/Medium -> Mas Robert
Ada references/documentation

## COMPARISON TABLE
Qs: How to compare & update the Integrated Planning Process, especially for Corridor:
[5 empty] | not yet | not yet
Mid-term | 12 Months | Key Qs | Current (according to docs v3) | Latest (to be checked) | References | to improve |  | Flow current (top to bottom) from each horizon
| Flow | What is the internal flow currently used for? |  |  |  |  | AM/Planning | FDP | full year, reservoir performance update
| Input | What is the input required for this plan horizon? |  | 1) Proposed activities and major milestones for the next 12 months 2) Mandatory safety, integrity, regulatory, and license-to-operate requirements 3) High-level capacity outlook and major resource constraints 4) Key risks, interfaces, and long lead items |  |  | AM/Planning | ADP | update as necessary
| Scope | What is the scope / level of detail this plan covers? (asset level, planner, etc.) |  | 1) Horizon: 12-months 2) List of task: - Activity classification - Readiness assessment -> high-level screening 3) Divided into different types of activities a) Mandatory -> maintain safety, asset integrity, compliance, license to operate b) Value adding -> generate operational, reliability, biz improvements |  |  | AM/Planning | LTP | cyclical/biannual
| Deliverables | What are the deliverables (documents, etc.) & contents needed for approval to be considered done? |  | Key Outputs: 1) Approved 12-Month integrated planning baseline 2) Early prioritization and protection of mandatory activities 3) Identification of major risks, constraints, and mitigation actions 4) Authorized feeder list for the 90-Day Planning process |  |  |  |  | 24 month - monthly
| Roles & approval (RACI) | Who is responsible for this plan / approval? |  | 1) VP Ops -> Chair 2) OIM, OM 3) Lead P&S 4) Integrated Planner 5) Key Ops, Maintenance, Project, and Support |  |  |  |  | 3rd year - quarterly
| Governance | How can we make sure this goes to plan? (change of controls, etc.) |  | Quarterly, w/ rolling updates as required |  |  |  |  | outer years - yearly
| Tools & system | What tools / system are used to execute / document this plan?
Short-term horizon | 90-days | Key Qs | Current (according to docs v3) | Latest (to be checked) | References | to improve |  | Flow current (top to bottom) from each horizon
| Flow | What is the internal flow currently used for? | 1) The 90-day is not a standalone plan — it operates as the look-ahead window within the combined 30/90-Day Operational Plan (Sec 2.3); 2) Activities that meet the entry criteria within the 90-day window are placed into the 90-Day plan; 3) Activities on the 90-Day plan (not yet on the 30-Day) have at least 30 days remaining to develop a complete work pack before they move into the frozen 30-day window; 4) The plan must pass the Readiness Gate Review before any activity enters the execution phase; 5) Note: Rev 3 provides no standalone 90-day flow diagram — the flow is described in narrative form (Sec 2.3) and Figure 2. |  |  |  | AM/Planning | FDP | full year, reservoir performance update
| Input | What is the input required for this plan horizon? | 1) Governed by the Acceptance / Input Criteria (Sec 5.1) and the Data Input Attribute table (Appendix D); 2) Gate requirements for an activity to enter the 90-Day plan (Sec 5.3): a) funding confirmed in the Medco LTP and annual WP&B; b) consent to proceed obtained from Partners and internal Medco; c) all permitting requirements obtained; d) engineering design sufficiently matured; e) execution contract available; f) materials readiness confirmed; g) SIMOPS (Simultaneous Operations) site-conflict check completed; h) HSE mitigation measures in place; 3) Materials must have confirmed delivery prior to the scheduled execution date — exceptions require OIM or Field Manager approval. | Key Inputs: 1) Screened activities from the 12 Month Plan 2) Activity classification (Mandatory, Value-Adding, Deferrable) 3) High level readiness outlook and capacity assessment 4) Key risks, SIMOPS exposure, and execution interfaces | Integrated Planning Process From Kang Oi |  | AM/Planning | ADP | update as necessary
| Scope | What is the scope / level of detail this plan covers? (asset level, planner, etc.) | 1) Operational planning horizon; covers all activities scheduled within the 90-day window; 2) Schedule level: AACE Level 3 (first activity-based planning, enabling critical-path analysis) (Sec 4); 3) Covers: a) field operations activities; b) non-operational functions (project FEL, drilling FEL, etc.); 4) Approved at Field Manager / Managers level (Table 1). | 1) Time Horizon: 90 days 2) List of task: - Activity classification - Readiness assessment 3) Categorized into different types of activities a) Mandatory b) Value adding c) Highlight biz event d) Deferrable e) Break-in 4) Activity is included in 12MO-plan already |  |  | AM/Planning | LTP | cyclical/biannual
| Deliverables | What are the deliverables (documents, etc.) & contents needed for approval to be considered done? | 1) Rev 3 does NOT explicitly define a deliverable or done-criteria per planning horizon; 2) The closest implied deliverable is an approved 90-Day plan with work packs developed 30 days before activities enter the frozen window; 3) Flag: this is a known gap — to be built as a new subsection in Rev 4 (see 6.8 of the document skeleton). | Key Outputs: 1) Approved 90-Day Plan (Gate 1 Approval) 2) Prioritized activity list for readiness validation 3) Management direction on trade-offs and deferrals 4) Authorized progression into the 30-Day Planning process |  |  |  |  | 24 month - monthly
| Roles & approval (RACI) | Who is responsible for this plan / approval? | 1) Overall plan approval: Field Manager / Managers (Table 1); 2) Planning Process Focal Point: Operations Planning & Scheduling (Table 1); 3) Planning Administrator: Functional / Asset Planner (Table 1); 4) Managers review and approve or reject plan changes within the 30-day frozen window (Sec 2.5); 5) Note: roles are written as prose in Sec 2.5, not in a RACI matrix format. | 1) VP Ops -> Chair 2) OIM, OM 3) Superntendent representatives 3) Lead P&S 4) Integrated Planner 5) Key Function Planners/Activity Coordinators |  |  |  |  | 3rd year - quarterly
| Governance | How can we make sure this goes to plan? (change of controls, etc.) | 1) The 90-day plan is governed by two gate reviews before execution entry: a) Sufficiency-of-Info Review; b) Readiness Gate Review; 2) All stakeholders are expected to provide timely updates on changes and participate in monthly planning meetings (Sec 2.3); 3) Top-down / bottom-up feedback loops across horizons (Sec 3); 4) TORs for meeting cadence are set out in Appendix B; 5) Change control applies primarily once work has moved into the frozen 30-day window (Sec 5.8 and Appendix F). | 1) Monthly (or as defined by asset needs) |  |  |  |  | outer years - yearly
| Tools & system | What tools / system are used to execute / document this plan? | 1) Rev 3 does NOT map tools or systems to a specific planning horizon — all system references are general; 2) Systems mentioned across the document that are likely relevant to 90-day execution: a) BPM (work order preparation and maintenance planning); b) SAP / Cost Centre (cost coding and tracking); c) SharePoint (plan storage and communication); d) MCRS (Management Control and Reporting System — KPIs); 3) Flag: a horizon-specific tool map does not exist in Rev 3.
| 30 days | Key Qs | Current (according to docs v3) | Latest (to be checked) | References | to improve |  | 7-day plan
| Flow | What is the internal flow currently used for? | 1) The first 30 days of an approved plan are 'frozen', issued monthly (Sec 5.2); 2) All work within the frozen window must be fully defined, with all preparatory work, equipment and resources confirmed available before the plan is issued; 3) If gate requirements are not met 30 days before planned commencement, the job is removed from the plan; 4) Note: no standalone 30-day flow diagram in Rev 3 — the frozen- window rules are described in Sec 5.2 and Sec 5.8.
| Input | What is the input required for this plan horizon? | 1) Gate requirements for the 30-Day plan (Sec 5.3): a) all materials and tools delivered to site and confirmed to meet required specifications; b) work pack (procedures, drawings, other documentation) complete and reviewed / approved; c) internal support resources confirmed and meeting all HSE requirements for mobilization; d) specialist vendor committed, with personnel details, schedule and mobilization date confirmed; e) materials and positions for stakeholder and government engagement confirmed and agreed; 2) Required activity data per item in the 30-Day plan (Sec 5.2): a) activity number and description; b) main work SAP / Cost Centre; c) task lead / responsible person for field work; d) man-hour estimates per operation and per resource; e) operation calendar (day-night shift, 24-hour, etc.); f) required start and end dates; g) optimistic, expected and pessimistic duration; h) functional location at order or operation level; i) number of personnel to mobilize, broken down by company (MEPG and contractors, including specialist support); j) number of expected field operations personnel support; k) contractor schedule confirmed ready; l) list of specific tools and equipment required from Operations (crane, scaffolds, boat, vehicles, etc.). | Key Inputs: 1) Prioritized activities from the approved 90 Day Plan 2) Detailed readiness status (scope, resources, materials, permits, SIMOPS, MOC) 3) Capacity utilization and execution constraints 4) Break-in proposals (if any)
| Scope | What is the scope / level of detail this plan covers? (asset level, planner, etc.) | 1) Operational horizon; the 30-day fixed / frozen window, issued monthly; 2) Covers fully defined, execution-ready activities only; 3) Schedule level: AACE Level 3 (field operations); AACE Level 4/5 for non-field functions under Plan Control (Sec 4); 4) Covers field operations and non-field functions (detailed day-to-day activity schedules); 5) Approved at Field Manager / Managers level (Table 1). | 1) Time Horizon: 30 days 2) List of task: - Activity classification - Readiness assessment 2) Categorized into different types of activities: a) Execution-Commitment - FROZEN b) Routine/BAU activities - NOT FROZEN
| Deliverables | What are the deliverables (documents, etc.) & contents needed for approval to be considered done? | 1) Rev 3 does NOT define explicit deliverables or done-criteria per planning horizon; 2) The closest implied deliverable is the approved frozen 30-Day plan with a complete work pack per activity; 3) Flag: known gap — to be built as a new subsection in Rev 4. | Key Outputs: 1) Approved 30 Day Plan (Gate 2 Approval) 2) Declaration of Frozen execution-commitment activities 3) Agreed execution sequence and resource allocation 4) Decisions on deferrals, constraints, and break-in requests
| Roles & approval (RACI) | Who is responsible for this plan / approval? | 1) Overall plan approval: Field Manager / Managers (Table 1); 2) Planning Process Focal Point: Operations Planning & Scheduling (Table 1); 3) Planning Administrator: Functional / Asset Planner (Table 1); 4) Changes within the frozen 30-day window route through: a) Plan Owner (for changes with no constraint impact); b) OIM (if the change impacts constraints); c) Field Manager (final approval for high-impact changes) (Sec 5.8); 5) Responsible Person / Job Owner ensures BPM Work Orders and planning input templates are accurate and up to date (Sec 2.5); 6) Note: roles described in prose (Sec 2.5), not as a RACI matrix. | - OIM (for plant activities) - chair - OM (for offsite activities) - chair - Superintendent - Activity Coordinators - Function Planners - HSE representatives (as required)
| Governance | How can we make sure this goes to plan? (change of controls, etc.) | 1) The 30-day frozen window is the primary governance mechanism for operational execution; 2) A 'change' to the approved 30-Day plan is defined as (Sec 5.8): a) adding work that requires additional resources or support; b) delays to tasks that impact constraints or other tasks; c) inclusion of activities requiring additional budget; d) other additions, cancellations or delays deemed substantial; 3) Change control process (Appendix F — PCR): a) Activity Sponsor submits PCR form to Asset Planner; b) if no major constraint impact → forwarded to Plan Owner; c) if major constraint impact → escalated to OIM / FM; 4) Daily / weekly operations meetings with Superintendent, OIM and Offsite Managers; changes documented via email or meeting minutes; 5) Deletion of an activity decided by the OIM after evaluating budget impact, resource reallocation and effect on other activities. | Monthly
| Tools & system | What tools / system are used to execute / document this plan? | 1) Rev 3 does NOT map tools to a specific planning horizon; 2) Systems implied for 30-day operational execution: a) BPM (work order management — PMs, CMs, work packs); b) SAP / Cost Centre (cost tracking and coding); c) PCR form (Appendix F — manual change request); 3) Flag: no per-horizon tool map in Rev 3.
| 7 days | Key Qs | Current (according to docs v3) | Latest (to be checked) | References | to improve
| Flow | What is the internal flow currently used for? | 1) Rev 3 does NOT define a 7-day planning horizon as a formal planning tier; 2) The only references to '7-day' in Rev 3 are: a) Plan Control uses a '7-D process' for structured field- operations oversight (Sec 2.3) — this is a control mechanism, not a standalone planning horizon; b) Appendix C lists a 7-day column, but only as a schedule- visualization granularity (Daily), not as a defined horizon; 3) OPEN DECISION — to be confirmed with Mas Fikri and Ops: a) Is 7-day a formal Corridor planning horizon in practice? b) Or is it a field-level execution / control tool within the 30-day frozen window? 4) Flag: no content can be grounded from Rev 3 until this is decided — do not fill from assumption.
| Input | What is the input required for this plan horizon? | 1) Rev 3 does not define inputs for a 7-day horizon; 2) Plan Control (the closest mapped concept) implies AACE Level 4/5 work-package detail — production of deliverable-level work packs (Sec 4) — but inputs are not enumerated; 3) Flag: unconfirmed — confirm with Ops planners. | 1) Approved frozen activities from the 30 Day Plan 2) Weekly execution readiness status 3) SIMOPS, lifting, scaffolding, and site coordination requirements 4) Labor availability versus planned workload
| Scope | What is the scope / level of detail this plan covers? (asset level, planner, etc.) | 1) Rev 3 does not define a 7-day scope; 2) The closest reference — Appendix C — maps 7-day to Daily schedule-visualization granularity only; 3) Plan Control is mapped to AACE Level 4 and 5 (deliverable-level work packs, execution / physical activities) (Sec 4); 4) Flag: scope cannot be defined until the formal-vs-granularity decision is made. | 1) Time Horizon: 7 days 2) List of task -> ONLY include the one who will be execution ready a) Activity classification. b) Readiness assessment - FINAL CHECK: - Scheduling - Operational - Labor 2) Categorized into different types of activities: - Routine PM - Execution Ready CM - Approved Major Activity - others, low-risk repetitive routine
| Deliverables | What are the deliverables (documents, etc.) & contents needed for approval to be considered done? | 1) Rev 3 does not define 7-day deliverables; 2) Flag: gap and unconfirmed horizon — cannot fill from the document. | Key Outputs: 1) Approved 7 Day Plan (Gate 3 Approval) 2) Final execution sequencing and daily work priorities 3) Identification of short-term risks and mitigation actions 4) Escalation of deviations or break-in needs
| Roles & approval (RACI) | Who is responsible for this plan / approval? | 1) If mapped to Plan Control, the applicable roles from Table 1 are: a) overall approval: Field Managers / supervisors; b) focal: Functional Planner; c) admin: Functional / Asset Planner; 2) But 7-day as a distinct horizon is not defined in Rev 3; 3) Flag: confirm who owns the daily / 7-day look-ahead in practice with Ops planners.
| Governance | How can we make sure this goes to plan? (change of controls, etc.) | 1) Rev 3 does not define governance for a 7-day horizon; 2) Plan Control uses the '7-D process' and comparable methods (e.g. MPEP requirements or other relevant methodologies) for day-to-day activity management (Sec 2.3); 3) Flag: confirm with Ops how the 7-day window is governed in practice (daily meetings, shift handover, toolbox talks, etc.). | Weekly
| Tools & system | What tools / system are used to execute / document this plan? | 1) Rev 3 does not map any tool to a 7-day horizon; 2) Flag: confirm with Ops planners what system (if any) is used to manage the daily / 7-day execution window.
Mid/Long-Term | 24-month plan | Key Qs | Current (according to docs v3) | Latest (to be checked) | References | to improve
| Flow | What is the internal flow currently looks like? | 1) The 24-Month Plan is the primary focus of Integrated Planning (Sec 2.3 — stated explicitly); 2) It takes the LTP (Level 1) and details it to Level 2 by Asset Management, Subsurface and other relevant functions; 3) It summarizes all activities between 90 days and 24 months; 4) Developed in parallel with the annual LTP budget cycle; 5) As needed, it may extend beyond 24 months to cover the full scope of major programs, including: a) key milestones; b) major activities; c) commercial and contractual requirements; d) rig moves; e) major procurement tenders; f) engine overhaul programs; g) shutdown schedules; 6) Note: no explicit 24-month flow diagram in Rev 3. | Moved as part of LTP already | Integrated Business Planning Guideline – E&P - ID-G-BU-GG0-GUI-GN-00-3005
| Input | What is the input required for this plan horizon? | 1) Governed by the Acceptance / Input Criteria (Sec 5.1); Tactical-level mandatory Appendix D subset includes: a) Department name and Activity Name; b) Location (field locations); c) Activity ID; d) Start and Finish dates; e) Plant Shutdown Needed; f) Impact LPO; g) POB Constraint; h) Total Number of People; i) Budgeted (Y/N) and Estimated Cost; j) Potential Consequences, Likelihood and Risk Ranks; 2) Inputs from: Asset Management, Subsurface, Operations, Projects, Well Operations, Commercial and supporting functions; 3) Inclusion thresholds from Appendix C apply at the 24-month level (e.g., major procurement events, major project milestones, well service and maintenance above $500K). |  | Integrated Business Planning Guideline – E&P - ID-G-BU-GG0-GUI-GN-00-3005
| Scope | What is the scope / level of detail this plan covers? (asset level, planner, etc.) | 1) Major-programs level — 90 days to 24 months (Sec 2.3); 2) Schedule level: AACE Level 2 (breakdown of Level 1, integration of major works across the lifecycle) (Sec 4); 3) Owned and approved at SVP level (Table 1); 4) Focal: Asset Management; Admin: Planning. |  | Integrated Business Planning Guideline – E&P - ID-G-BU-GG0-GUI-GN-00-3005
| Deliverables | What are the deliverables (documents, etc.) & contents needed for approval to be considered done? | 1) Rev 3 does not define explicit deliverables or done-criteria per planning horizon; 2) Implied deliverable: an approved integrated 24-Month schedule covering major programs; 3) Flag: known gap — to be built as new content in Rev 4. |  | Integrated Business Planning Guideline – E&P - ID-G-BU-GG0-GUI-GN-00-3005
| Roles & approval (RACI) | Who is responsible for this plan / approval? | 1) Overall Plan Approval: SVP (Table 1); 2) Planning Process Focal Point: Asset Management (Table 1); 3) Planning Administrator: Planning (Table 1); 4) SVP holds accountability for their respective functions in delivering to the Plan Owner (Sec 2.5); 5) Note: the SVP role in Sec 2.5 also says the SVP approves the 10-Year Plan — inconsistency with Table 1 (which gives this to the COO); this must be resolved. |  | Integrated Business Planning Guideline – E&P - ID-G-BU-GG0-GUI-GN-00-3005
| Governance | How can we make sure this goes to plan? (change of controls, etc.) | 1) The 24-Month Plan is governed by the P&S Steering Committee and the SVP's accountability framework (Sec 2.5); 2) TORs for the Tactical planning meetings (Appendix B); 3) The annual LTP / Budget cycle serves as the primary trigger for the 24-month refresh (Sec 2.3 and Sec 8); 4) Both the 10-Year and 24-Month Plans are developed in parallel with the annual LTP budget cycle (Sec 2.3). |  | Integrated Business Planning Guideline – E&P - ID-G-BU-GG0-GUI-GN-00-3005
| Tools & system | What tools / system are used to execute / document this plan? | 1) Rev 3 does not map tools to a specific planning horizon; 2) Systems implied for 24-month planning: a) SharePoint — summary plans stored centrally for broad access (Sec 5.7); b) ARIS — business process maps for governance reference; 3) Flag: the scheduling or integrated planning tool used to build and maintain the 24-month plan is not named. |  | Integrated Business Planning Guideline – E&P - ID-G-BU-GG0-GUI-GN-00-3005
| Long Term Plan (LTP) | Key Qs | Current (according to docs v3) | Latest (to be checked) | References | to improve
| Flow | What is the internal flow currently used for? | 1) The LTP is a Level 1 milestone plan typically spanning 10 or more years (Sec 2.3); 2) It is aligned with and developed in parallel with the annual budget cycle; 3) Baselines and performance are monitored and assessed against the Asset's annual goals/target through Outlook monitoring through MPR with BA E&P Planning as the owner, supported by E&P Finance from data 4) The 24-Month Plan is the next level down, developed by Asset Management, Subsurface and relevant functions from the LTP (Sec 2.3); -> TAKEN OUT IN MEDCO CURRENT PLAN 5) Note: no explicit LTP flow diagram in Rev 3 — described in narrative form and Figure 2. |  | Integrated Business Planning Guideline – E&P - ID-G-BU-GG0-GUI-GN-00-3005
| Input | What is the input required for this plan horizon? | 1) Governed by the Acceptance / Input Criteria; the Strategic- level mandatory subset of Appendix D applies: a) Department name; b) Activity Name and Activity ID; c) Plant Shutdown Needed; d) Impact LPO (production loss); e) POB Constraint; f) Total Number of People; g) Budgeted (Y/N) and Estimated Cost; h) Potential Consequences, Likelihood and Risk Ranks; 2) Cost-phasing data from the LTP / forecasting cycle (Sec 8); 3) Informed by inventory-generation initiatives, economic valuations and POD reviews (Appendix A); 4) Inclusion thresholds from Appendix C apply (e.g., major procurement events above $20M, major project milestones above $75M). | Simple: 1) Activity-nya apa 2) Impact to Cost/Production spt apa Production from subsurface + (from asset: update DOE assumption, commercial assumption) + GHG emmision from HSE + reserve assessment Yang quarterly udah nggak ada, to provide timeframe: 2 tahun kedepan + current years (monthly) -> sisanya yearly | Integrated Business Planning Guideline – E&P - ID-G-BU-GG0-GUI-GN-00-3005
| Scope | What is the scope / level of detail this plan covers? (asset level, planner, etc.) | 1) Asset-level coverage (Table 1); 2) Schedule level: AACE Level 1 — key milestones and summary activities only (Sec 4); -> OPAA's scope 3) Horizon: 10 or more years; 4) Developed in parallel with the annual budget cycle; 5) Focus: annual goals, performance baselines and milestone monitoring. |  | Integrated Business Planning Guideline – E&P - ID-G-BU-GG0-GUI-GN-00-3005 Additional OPAA procedures
| Deliverables | What are the deliverables (documents, etc.) & contents needed for approval to be considered done? | 1) Rev 3 does not define explicit deliverables or done-criteria per horizon; 2) Appendix A describes the LTP 10+ component as including: a) economic valuations; b) POD (Plan of Development) management within existing PSCs; c) annual review in preparation for the LTP process; | 1) Planning side: - provide 10y+ plan for more -> approved by BOD: check input/scope for docs needed - budget next year alr. provided (final deliverability) | Integrated Business Planning Guideline – E&P - ID-G-BU-GG0-GUI-GN-00-3005
| Roles & approval (RACI) | Who is responsible for this plan / approval? | 1) Overall Plan Approval: COO (Table 1); 2) Planning Process Focal Point: Asset Management (Table 1); 3) Planning Administrator: Planning (Table 1); 4) Component accountability (Appendix A): a) COO owns the LTP; b) Asset Management, E&P Planning and Business Analysis are accountable for collecting and supporting the LTP; 5) IMPORTANT — inconsistency inside Rev 3 itself: a) Table 1 assigns LTP (10-Year) approval to the COO; b) Sec 2.5 states the SVP 'approves the 10-Year and 24-Month Plans'; c) This conflict must be resolved in the rebuild. | RACI is already included -> POV all function related in this As per OPAA's POV | Integrated Business Planning Guideline – E&P - ID-G-BU-GG0-GUI-GN-00-3005
| Governance | How can we make sure this goes to plan? (change of controls, etc.) | 1) Annual validation and review; revisited as needed when significant political, market or commercial events arise (Appendix A); 2) Reviewed by the Leadership Team (LT) at least annually (for the Long-Term Growth component) (Appendix A); 3) Aligned with the Corporate-BU strategy cycle; TORs for Strategic meetings are in Appendix B (Sec 8); 4) Annual LTP and Forecasting Planning Calendar serve as triggers for timing adjustments (Sec 8); 5) Reviewed collaboratively by Asset Management, E&P Planning and Business Analysis teams (Sec 8). | - Forecast monitoring through: a) MPR - STPF -> MEPG's side - Outlook Cost - any update between cycle for change of control (how-to's update -> OPAA/AM?) b) QPR c) Weekly Report BOD -> specific for volume | Integrated Business Planning Guideline – E&P - ID-G-BU-GG0-GUI-GN-00-3005
| Tools & system | What tools / system are used to execute / document this plan? |  | 1) E&P Planning -> BPM -> IBP system 2) OPAA's drive/AM plan for LTP | Integrated Business Planning Guideline – E&P - ID-G-BU-GG0-GUI-GN-00-3005
| Asset Dev. Plan (ADP) | Key Qs | Current (according to docs v3) | Latest (to be checked) | References | to improve
| Flow | What is the internal flow currently used for? | 1) The BU Life / Asset Development Plan is a comprehensive set of documents outlining strategic alternatives and development scenarios for the Medco Asset (Sec 2.3); 2) It reflects the Vision and Mission of MEPG; 3) Four components, each with its own ownership and storage (Appendix A): a) Strategy Development & Scenario Planning (CDQ session, yearly or as needed, Q4, owned by COO); b) Long-Term Growth Plan (minimum yearly, Q1, owned by COO); c) LTP 10+ years (yearly, Q3, owned by COO); d) End-of-Life Strategy (yearly, timing varies by PSC, owned by SVP); 4) Aligns all groups and departments with the Asset's strategic goals and identifies milestones to achieve those objectives; 5) Note: no dedicated ADP flow diagram in Rev 3. |  | Asset Development Plan (ADP) Guideline - GL-2/6.2021/MEDC/RESV-TA
| Input | What is the input required for this plan horizon? | 1) Corporate methodologies and CDQ (Collaborative and Decision Quality) sessions are used as inputs (Appendix A); 2) Inputs include: a) corporate-BU strategy alignment; b) new-opportunities selection criteria; c) economic valuations as part of the LTP process; d) market influences, exit strategies, key drivers; 3) Strategic-level Appendix D attributes apply; 4) The plan is triggered or revisited by significant political, market or commercial events (Appendix A). |  | Asset Development Plan (ADP) Guideline - GL-2/6.2021/MEDC/RESV-TA
| Scope | What is the scope / level of detail this plan covers? (asset level, planner, etc.) | 1) Business Unit level (Table 1) — the longest planning horizon; 2) Covers: a) strategic alternatives and development scenarios; b) scenario planning, long-term growth / divestment planning; c) end-of-life strategies for assets (ASR); 3) Owned by the COO, supported by the SVP for Portfolio Management; 4) Reflects the Vision and Mission of MEPG. |  | Asset Development Plan (ADP) Guideline - GL-2/6.2021/MEDC/RESV-TA
| Deliverables | What are the deliverables (documents, etc.) & contents needed for approval to be considered done? | 1) Rev 3 does not define explicit deliverables or done-criteria per planning horizon; 2) Appendix A describes the four ADP components with ownership and storage, but not a formal approval definition; 3) Related content: a) Abandonment and Site Restoration (ASR) strategy is the deliverable for the End-of-Life component; b) Long-Term Growth Plan document maintained by Planning; 4) Flag: partial — components are given but done-criteria are not. |  | Asset Development Plan (ADP) Guideline - GL-2/6.2021/MEDC/RESV-TA
| Roles & approval (RACI) | Who is responsible for this plan / approval? | 1) Overall Plan Approval: COO (Table 1); 2) Planning Process Focal Point: Asset Management (Table 1); 3) Planning Administrator: See Appendix B (Table 1); 4) Component accountability (Appendix A): a) COO — owns Strategy, Long-Term Growth and LTP 10+; b) SVP — owns the End-of-Life strategy; c) Asset Management — collecting and supporting development of long-term growth opportunities; d) E&P Planning and Business Analysis — accountable for LTP 10+; 5) The COO is supported by the SVP for Portfolio Management. |  | Asset Development Plan (ADP) Guideline - GL-2/6.2021/MEDC/RESV-TA
| Governance | How can we make sure this goes to plan? (change of controls, etc.) | 1) The ADP Strategy component undergoes annual validation and review with the corporate team (Appendix A); 2) The Long-Term Growth Plan is reviewed by the Leadership Team (LT) at least annually (Appendix A); 3) Revisited as needed in response to significant political, market or commercial events; 4) TORs for Strategic meetings in Appendix A and B; 5) Documents are confidential and maintained by the Planning team. |  | Asset Development Plan (ADP) Guideline - GL-2/6.2021/MEDC/RESV-TA
| Tools & system | What tools / system are used to execute / document this plan? | 1) Rev 3 does not map specific tools to the ADP; 2) Storage per component (Appendix A): a) Strategy / Scenario → Confidential SharePoint (Advisor-owned); b) Long-Term Growth → Confidential Drive (BD-owned); c) LTP 10+ → Confidential Drive (Finance-owned); d) End-of-Life → Confidential SharePoint (AM-owned); 3) Flag: the modelling or scenario-planning tool is not named. |  | Asset Development Plan (ADP) Guideline - GL-2/6.2021/MEDC/RESV-TA
| Field Depletion Plan (FDP) | Key Qs | Current (according to docs v3) | Latest (to be checked) | References | to improve
| Flow | What is the internal flow currently used for? | 1) Rev 3 does NOT contain or define a 'Field Depletion Plan (FDP)'; 2) The long-term development artifacts in Rev 3 are: a) ADP (BU Life Plan); b) LTP (10-Year / Long-Term Plan); c) Plans of Development (POD) within existing PSCs; d) End-of-Life / ASR (Abandonment and Site Restoration) strategy; 3) OPEN DECISION — confirm with Mas Fikri whether FDP is: a) a Corridor-specific informal plan not yet in the guideline; b) equivalent to the POD or the End-of-Life strategy; c) genuinely new content to be added in Rev 4; 4) Flag: this column cannot be filled from Rev 3 — no basis exists. |  | Field Depletion Plan (FDP) Guidelines - GL-001/06.202/MEDC/RESV-TA
| Input | What is the input required for this plan horizon? | 1) Rev 3 does NOT contain or define a 'Field Depletion Plan (FDP)'; 2) The long-term development artifacts in Rev 3 are: a) ADP (BU Life Plan); b) LTP (10-Year / Long-Term Plan); c) Plans of Development (POD) within existing PSCs; d) End-of-Life / ASR (Abandonment and Site Restoration) strategy; 3) OPEN DECISION — confirm with Mas Fikri whether FDP is: a) a Corridor-specific informal plan not yet in the guideline; b) equivalent to the POD or the End-of-Life strategy; c) genuinely new content to be added in Rev 4; 4) Flag: this column cannot be filled from Rev 3 — no basis exists. |  | Field Depletion Plan (FDP) Guidelines - GL-001/06.202/MEDC/RESV-TA
| Scope | What is the scope / level of detail this plan covers? (asset level, planner, etc.) | 1) Rev 3 does NOT contain or define a 'Field Depletion Plan (FDP)'; 2) The long-term development artifacts in Rev 3 are: a) ADP (BU Life Plan); b) LTP (10-Year / Long-Term Plan); c) Plans of Development (POD) within existing PSCs; d) End-of-Life / ASR (Abandonment and Site Restoration) strategy; 3) OPEN DECISION — confirm with Mas Fikri whether FDP is: a) a Corridor-specific informal plan not yet in the guideline; b) equivalent to the POD or the End-of-Life strategy; c) genuinely new content to be added in Rev 4; 4) Flag: this column cannot be filled from Rev 3 — no basis exists. |  | Field Depletion Plan (FDP) Guidelines - GL-001/06.202/MEDC/RESV-TA
| Deliverables | What are the deliverables (documents, etc.) & contents needed for approval to be considered done? | 1) Rev 3 does NOT contain or define a 'Field Depletion Plan (FDP)'; 2) The long-term development artifacts in Rev 3 are: a) ADP (BU Life Plan); b) LTP (10-Year / Long-Term Plan); c) Plans of Development (POD) within existing PSCs; d) End-of-Life / ASR (Abandonment and Site Restoration) strategy; 3) OPEN DECISION — confirm with Mas Fikri whether FDP is: a) a Corridor-specific informal plan not yet in the guideline; b) equivalent to the POD or the End-of-Life strategy; c) genuinely new content to be added in Rev 4; 4) Flag: this column cannot be filled from Rev 3 — no basis exists. |  | Field Depletion Plan (FDP) Guidelines - GL-001/06.202/MEDC/RESV-TA
| Roles & approval (RACI) | Who is responsible for this plan / approval? | 1) Rev 3 does NOT contain or define a 'Field Depletion Plan (FDP)'; 2) The long-term development artifacts in Rev 3 are: a) ADP (BU Life Plan); b) LTP (10-Year / Long-Term Plan); c) Plans of Development (POD) within existing PSCs; d) End-of-Life / ASR (Abandonment and Site Restoration) strategy; 3) OPEN DECISION — confirm with Mas Fikri whether FDP is: a) a Corridor-specific informal plan not yet in the guideline; b) equivalent to the POD or the End-of-Life strategy; c) genuinely new content to be added in Rev 4; 4) Flag: this column cannot be filled from Rev 3 — no basis exists. |  | Field Depletion Plan (FDP) Guidelines - GL-001/06.202/MEDC/RESV-TA
| Governance | How can we make sure this goes to plan? (change of controls, etc.) | 1) Rev 3 does NOT contain or define a 'Field Depletion Plan (FDP)'; 2) The long-term development artifacts in Rev 3 are: a) ADP (BU Life Plan); b) LTP (10-Year / Long-Term Plan); c) Plans of Development (POD) within existing PSCs; d) End-of-Life / ASR (Abandonment and Site Restoration) strategy; 3) OPEN DECISION — confirm with Mas Fikri whether FDP is: a) a Corridor-specific informal plan not yet in the guideline; b) equivalent to the POD or the End-of-Life strategy; c) genuinely new content to be added in Rev 4; 4) Flag: this column cannot be filled from Rev 3 — no basis exists. |  | Field Depletion Plan (FDP) Guidelines - GL-001/06.202/MEDC/RESV-TA
| Tools & system | What tools / system are used to execute / document this plan? | 1) Rev 3 does NOT contain or define a 'Field Depletion Plan (FDP)'; 2) The long-term development artifacts in Rev 3 are: a) ADP (BU Life Plan); b) LTP (10-Year / Long-Term Plan); c) Plans of Development (POD) within existing PSCs; d) End-of-Life / ASR (Abandonment and Site Restoration) strategy; 3) OPEN DECISION — confirm with Mas Fikri whether FDP is: a) a Corridor-specific informal plan not yet in the guideline; b) equivalent to the POD or the End-of-Life strategy; c) genuinely new content to be added in Rev 4; 4) Flag: this column cannot be filled from Rev 3 — no basis exists. |  | Field Depletion Plan (FDP) Guidelines - GL-001/06.202/MEDC/RESV-TA