| Document Title | : | Procedure/Work Instruction/Job Note: Medco E&P Grissik Integrated Planning & Scheduling Guideline |
| --- | --- | --- |
| MEPG Doc No. | : | ID-G-BU-GG0-PRO-GN-00-0053 |

Originator: Medco E&P Grissik Ltd. Information Owner: 514018 – Asset Management Corridor Area: BU - Business Unit Location: GN - General System: 00 - General Systems Document Type: PRO - Procedure / Work Instruction / Job Note Discipline / Sub discipline: G - General / G0 - General Old Document No.: -

| 4 | IFU | Nov 22, 2024 | Issued for Use |  | M. Ridho Z.K | Fikri M. H. | Jumadil Kubro | Jumadil Kubro | Tri Laksono |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3 | IFU | Nov 22, 2024 | Issued for Use |  | Fikri M. H. | Jumadil Kubro | Jumadil Kubro | Jumadil Kubro | Tri Laksono |
| 2 | IFU | Aug 01, 2015 | Issued for Use |  | J. Sitter | Dirk F. | Ali M. | Rismal A. | Mark P. |
| 1 | IFU | Dec 12, 2013 | Issued for Use |  | Tri L. | John V. | Ali M. | Tim W. | Taufik A. |
| Rev | Status | Issue Date | Reason for Issue |  | Prepared | Checked | Information Owner | Sr. Manager | SVP |
|  |  |  |  |  |  |  | Approvals |  |  |

Printed initials in the approval boxes confirm that the document has been signed.

The originals are held within Document Management.

|  |  | Revision Sheet |  |
| --- | --- | --- | --- |
| REVISION | DATE | DESCRIPTION OF CHANGE |  |
| 1 | 12 December 2013 | Issued for Use |  |
| 2 | 01 August 2015 | - Add reference to Appendix K&L (ToC) - Delete Figure 2 (section 2,3) – redundant with work process maps - Delete Figure 4 (Section 2.3) – redundant figure with Appendix C - Delete Figure 5 (Section 3) – redundant with MCRS - Delete MCRS (section 6.4) – redundant with section 3 - Delete section 12 (page 27) – redundant with ToC - Updated Section 1 to realign with global RP OE-P&S-RP-002 - Updated Section 2.2 – minor realignment of strategy - Updated Section 2.3 – alignment with updated horizons - Updated Section 3 – removed figure for MCRS and Process relationship (linked in Appendix C), deleted sections detailing planning structure (redundant with section 4) - Updated Section 4 – deleted details of each horizon (redundant with Section 2.3 and Appendix E) summarized details only. - Section 5 general updates to improve clarity - Section 5.5 - Revised section to address low priority practices for COPI (OE practice 3.201-3.203) deleted section in 5.5.3 on steps to resolving conflicts (superfluous) - Section 5.6.4 plan briefing for operations. Not required in a BU level guideline - Section 6.2 changed to business performance review (formerly assessment and audit) - Section 6.4 (defect elimination) deleted, redundant with business process review and AAR’s - Section 6.x (Value tracking) not implemented in COPI and not a requirement under the OE framework - Section 7 – replaced aspirational ‘feel-good’ statements with specific actions for continuous improvement - Sections 6, 8 9, 10,11 – general updates to align with actual BU practices and OE framework - Appendix A – Deleted definitions, redundant with text of document; replaced with P&S SharePoint Overview - Appendix B – Delete redundant business process maps and replace with BU Life Planning - Appendix C – Deleted original Business Process maps, redundant with updated business process maps. Replace with current business processes. - Appendix F – Updated index to correct name “Data Input Attribute” - Appendix G – deleted strategic and tactical prioritization matrices. OE practice 3.201/202/203 considered low value for COPI - Appendix L – Delete, revised and moved to body of document (section 6.4) - General formatting and typo corrections |  |
| 3 | 22 November 2024 | - Update the word of LRP into LTP, aligned with Medco implementation. - Update Section 1.1 - Removed the reference of Global Recommended Practice for Integrated Planning (OE-P&S-RP-002). - Update Section 1.2 - The kind of Planning and Scheduling Activities aligned with Medco implementation, namely BU Life/Asset Development Plan (ADP), 10-Year/Long-Term Plan (LTP), Medium/Tactical/24-Month Plan, Short-Term/Operational/30-90 Day Plan, and detailed operational-level planning. - Update Section 2.2 - Removed the Development and Exploration & BD on the explanation of specific function that may incorporate tailored practices for P&S. - Update Section 2.3 - Aligned with updated Section 1.2. - Update Figure 2 - Aligned with updated Section 1.2 & 2.3 - Update Section 2.5 and Tabel 1 - Aligned the role with Medco implementation - Update Section 3 - Removed the reference file - Update Section 3.1 - Aligned the reference appendices due to the change in the Appendices - Update Section 4 - Aligned with updated Section 1.2, 2.3, and Figure 2 - Update Section 5 - Aligned the reference appendix from Appendix F to Appendix D, Appendix I to Appendix F. - Update Section 5.6 - Added more detailed explanation about the term. - Update Section 6 - Aligned the reference appendix from Appendix J to Appendix G. - Update Section 6.5.1 - Changed the title section from Plan Attainment to Schedule Attainment and its explanation including the equation. - Update Section 6.5.2 - Change the title section from Addition-to-Plan to SPI (Schedule Performance Indicator) and its explanation including the equation. - Update Section 6.5.3 - Change the title section from Deletion-of-Plan to Plan Break-in and its explanation including the equation. - Add new Section 6.5.4 Plan Deletion - Update Section 6.6 - Removed the key area addressed "Assessment against OE Framework" and aligned with Medco implementation. - Update Table P&S system Reviews and Assessments - Aligned the reference Appendix from Appendix C to Appendix A. - Removed Section 7.3 and 7.4 - Update Section 8 - Aligned the Planning Cycle review with Medco implementation. - Updated the Appendices - Remove the Appendix A due to irrelevant with Medco implementation. - Update the Appendix B - Changed the tilte (orderly named) into Appendix A and aligned the role with Medco implementation. - Remove the Appendix C due to irrelevant with Medco implementation - Update the Appedix D - Changed the tilte (orderly named) into Appendix B and updated with the new TOR - Update the Appendix B - Changed the tilte (orderly named) into Appendix C and aligned the role with Medco implementation. - Update the Appendix F - Changed the tilte (orderly named) into Appendix D and aligned the role with Medco implementation. - Update the Appendix G - Changed the tilte (orderly named) into Appendix E and aligned the role with Medco implementation. - Update the Appendix H - Changed the tilte (orderly named) into Appendix F and aligned the role with Medco implementation. - Update the Appendix I - Changed the tilte (orderly named) into Appendix G and aligned the role with Medco implementation. - General formatting and typo corrections |  |

Additional Approvers (If Applicable)

| Name | Designation | Signature | Date |
| --- | --- | --- | --- |
| Fahmi A. Syafri | Manager OPAA |  |  |
| Oi Rozak | Lead P&S |  |  |
| Rosa V. Damayanti | Manager PDC Planning |  |  |
| Robert Cahyadi | Manager Planning |  |  |

# Contents

Contents	5

Appendices	6

1	Introduction	7

1.1	Concept and Objectives of Integrated Planning	7

1.2	Scope	9

2	Planning System	10

2.1	Integrated Planning Philosophy	10

2.2	Integrated Planning Strategy	10

2.3	Integrated Planning Work Process	12

2.4	Plan Ownership and Approval	18

2.5	Roles and Responsibilities	19

3	Governance Model	22

3.1	Meeting Term of Reference	22

4	Criteria of Activities Inclusion into Plan	23

5	Managing the Plans	24

5.1	Acceptance/Input Criteria	24

5.2	30/90 Day Plan	24

5.3	Gate Review Criteria	25

5.4	Managing Constraints	25

5.5	Risk Assessment	27

5.6	Conflict Resolution and Plan Prioritization	28

5.7	Administering the Plan	29

5.8	Change Control for Operational Planning Horizon	30

6	Assessing Performance	31

6.1	Debriefing and After Action Reviews (AAR)	31

6.2	Planning Compliance	31

6.3	Peer Review	31

6.4	Business Performance Review	32

6.5	Key Performance Indicator (KPI)	32

6.6	Benchmarking Strategy	34

7	Planning Process Review and Adjustment	36

7.1	Continuous Improvement	36

7.2	Reviews and Assessments	36

8	Alignment with Operating Cost Management	36

9	Future State – Dynamic Plan Management	36

Appendices	37

# Appendices

Appendix A – BU Life Planning	37

Appendix B – Meeting Term of Reference	38

Appendix C – Planning Activity Inclusion Criteria	39

Appendix D – Data Input Attribute	44

Appendix E – Prioritization Matrix for Operational Horizon	48

Appendix F – Activity Change Request Process	49

Appendix G – Conducting After Action Review	52

# Introduction

## Concept and Objectives of Integrated Planning

The purpose of this document is to outline the processes and governance for Integrated Planning at Medco E&P Grissik Ltd (MEPG). Integrated Planning is a set of cross-functional processes designed to combine, sequence, and coordinate all activities across short-term (Operational), medium-term (Tactical), and long-term (Strategic) Horizons within the Medco Asset Plan1.

The goal is to produce an approved and prioritized planning and scheduling process that maximizes stakeholder value by efficiently identifying critical activities, resolving conflicts, and managing opportunities. These processes are designed to minimize siloed thinking and promote a collaborative approach to planning.

Table 1. Integrated Planning Objectives, Expected Behaviours, and Organizational Value

| No. | Objective (goal) |  |  | Expected Behaviour (how) |  | Organizational Value (why) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Enhance HSE Performance |  |  | Proactively identify HSE risks, constraints, and readiness |  | Safer operations through fewer HSE incidents. |  |  |
| 2 | Increase MEPG value as MEPI’s asset. |  |  | Identify critical activities, resolve conflicts, and prioritize opportunities |  | Improved value creation from Asset development. |  |  |
| 3 | Enable Informed Decision-Making |  |  | Use reliable and timely planning to support decision making. |  | Better and faster operational and business decisions. |  |  |
| 4 | Improve Cost and Resource Efficiency |  |  | Coordination of manpower, contractors, equipment, across activities. |  | Improved resource utilization and costs efficiency |  |  |
| 5 | Improve Planning Performance |  |  | Review planning performance and learn from execution results. |  | More reliable plans and continuous improvement. |  |  |
| 6 | Support Production Performance |  |  | Align activities to minimize downtime and capture opportunities. |  | Improved production capacity and delivery to buyer. |  |  |
| 7 | Improve Cross-Functional Communication |  |  | Share plans, goals, constraints and changes across relevant functions. |  | Reduced conflicts and improved activity integration |  |  |
| 8 | Establishing a Common Planning Framework |  |  | Use the same, agreed upon planning process, accountabilities, and business priorities |  | Consistent planning and shared view across MEPG assets. |  |  |
| 9 | Ensure Workforce and Role Alignment |  |  | Understand and execute defined planning roles and accountabilities across planning horizons. |  | Clear ownership and alignment toward Asset objectives |  |  |
| 10 | Improve Execution Readiness and Delivery |  |  | Confirm key scope, materials, contract, and resources before execution. |  | More reliable and on-time field execution for activities. |  |  |
| 11 | Minimize Non-Productive Time |  |  | Improve work preparation, sequencing, and manpower coordination. |  | Reduced waiting time and manpower inefficiency. |  |  |

Achievement of the Integrated Planning objectives shall be monitored through the applicable planning and performance indicators as defined in Section x.x – Key Performance Indicators (KPI).

The integrated planning processes shall be applied consistently across all functions and disciplines within MEPG to provide common framework for collaboration, establish alignment/understanding across planning horizons, and set clear expectations for all stakeholders involved.

_________________________

1Within this document, items are referred to and interchanged as BU life / Asset Development Plan (ADP), 10-year plan / Long Term Planning (LTP), Medium or Tactical or 24-Month plan, Short-Term Production Forecast (STPF) and the Operational or 30/90-day plan.

Figure 1.   Integrated Planning Concept

## Scope

The guidelines apply to the Integrated Planning and Scheduling (P&S) activities for MEPG Asset-operated PSCs, Exploration, and Development activities. It covers the integration and alignment of planning activities across the following planning horizons and processes:

- Asset Development Plan (ADP);

- Field Depletion Plan (FDP);

- Long-Term Plan (LTP), which includes the 24-month and outer-years planning processes;

- Short-term Planning, which includes 12-month, 90-day, 30-day and 7-day planning processes.

This guideline is meant to establish the planning principles, processes, and governance required to integrate activities across relevant MEPG functions and disciplines. Function-specific planning and execution practices shall remain governed by their respective applicable procedures and guidelines, while maintaining alignment with relevant scope of requirements established in this guideline.

# Philosophy & Principles

## Integrated Planning Philosophy

At MEPG, Integrated Planning uses a cross-functional and collaborative approach to align activities across three planning horizons: (1) Strategic, (2) Tactical, and (3) Operational. Activities are integrated and prioritized based on risk, business value, readiness, and available resources to support informed decision-making and effective execution.

Integrated Planning provides a common framework to align functions and identify constraints, opportunities, and ownership early in the planning process. The process aims to produce coordinated, resourced, prioritized, and approved plans and schedules, while continuously improving planning and execution performance.

## Integrated Planning Strategy

- Organization and Ownership.

Planning process in MEPG shall be supported by competent planning resources at both the Asset and Functional levels. Each planning time horizon (strategic, tactical, and operational) shall have clearly defined ownership, responsibilities, and authority of approvals.

- Goal Alignment

All MEPG Assets, Functions, and relevant stakeholders shall align their activities with agreed short, medium, and long-term agreed-upon business goals and Planning and Scheduling (P&S) objectives.

- Integrated Planning and Scheduling.

All activities within MEPG asset, including contractors, shall be planned, scheduled, and assessed in alignment with the Integrated Planning process.

- Integration Across Planning Horizon

The Strategic, Tactical, and Operational horizons shall remained aligned. Any changes of plan, priorities, and decisions shall be communicated and assessed between horizon to maintain consistency from long-term planning to field execution.

- Planning tools, visualization and communication.

Planning tools, visualization and communication methods shall provide clear and consistent planning information. The methods use may be adjusted to meet stakeholders needs while maintaining a common view of the Planning & Scheduling (P&S) objectives.

- Continuous Improvement.

Regular and consistent reviews of planning performance shall be conducted to identify gaps, capture lesson learned, refine and maintain the relevancy of business processes.

- Structured Planning Process.

Each planning horizon shall adhere to a structured business process, which includes:

- Integration of activities across different functions to ensure a unified approach.

- Establishment of a baseline plan that accounts for key constraints, synergies, and potential conflicts for each time horizon.

- Differentiation between activities requires high certainty and strict control from activities that can remain flexible for future adjustments.

- Formal

- approval of the integrated plan by the designated ownership level for each planning horizon.

- Feedback and alignment mechanisms between planning horizons to ensure changes in one horizon are reflected in the others where needed.

- Regular review of planning performance to identify gaps, and opportunities for continuous improvement.

## Function-Specific Practices

In addition to Integrated Planning Principles mentioned in section 2.2 that apply across MEPG, certain functions may apply tailored practices for P&S. These practices shall remain aligned with this guideline and function’s own procedures and standards.

- Operations

- Shutdown Planning.  Shutdown activities shall be coordinated with other functional activities and aligned with the maintenance schedules of both internal and external stakeholders, including buyers.

- Projects

- Portfolio Management and Operability Execution.  The portfolio management of facilities and wells, from the pre-development through to execution, including contractor activities, shall follow the Integrated Planning process and comply with the applicable Medco Project Excellence Process (MPEP)

- Operability Assurance (OA). Operability assurance shall support operations engagement in portfolio management, facilitating adequate input during project development. During execution, the Operations Readiness Review process will support operations teams in preparation for startup, ensuring seamless handover and project closeout phases.

- Well Operations and Services

- Procurement Planning. Procurement activities shall commence early during the strategic planning phase to account for possible and contingencies in the tactical period.

- Well Delivery and Drilling Plan (WDDP). This processes shall be utilized to establish and regularly review baseline plans, with the objective of minimizing late-stage changes.

- Commercial

- Sales Agreement Alignment. Contractual events, rights, and obligations outlined in each sales agreement shall be integrated across relevant functions to optimize, protect, and/or create value for the company.

- Market Alignment. Market drivers shall be regularly reviewed and reflected in production planning to to keep P&S aligned with commercial conditions.

# Planning System & Horizon

MEPG Integrated Planning connects long-term Asset planning with short-term operational planning and field execution. The planning system consists of different planning horizons, with the level of detail, readiness, and planning certainty increasing as activities move closer to execution.

Each planning horizon is connected and should not be managed independently. Changes in Asset priorities, assumptions, constraints, or activity status may require review and alignment across related planning horizons. The planning horizons and their relationship are described in Section 3.1 below.

## Horizon Breakdown

The MEPG Integrated Planning system covers the following planning processes and horizons:

- Field Depletion Plan (FDP)

The Field Depletion Plan (FDP) provided the integrated technical basis for field depletion and development planning. It is prepared at field level and integrated relevant subsurface, wells, facilities, operations, and other technical considerations.  The FDP process and approval requirements shall follow the applicable Medco Field Depletion Plan Guideline (Doc. No: GL-001/06.2021/MEDC/RESV-TA).

The FDP processes reviews field and reservoir performance, reserves and resources, production outlook, depletion and operational strategies, existing and future well activities, surveillance requirements, facility requirements, and technical feasibility. The resulting technical evaluation and identified opportunities provide inputs to the Asset Development Plan (ADP).

- Asset Development Plan (ADP)

The Asset Development Plan (ADP) is created to establish the long-term development direction of the Asset. It builds on the FDP and integrates technical, commercial, economic, and business considerations at Block or Asset level. The ADP process and approval requirements shall follow the applicable Asset Development Plan Guideline (No. GL-002/06.2021/MEDC/RESV-TA).

The ADP processes reviews: 1) Asset scenario planning, 2) long-term growth 3) divestment planning, 4) end-of-life, 5) resource base & development options, 6) production profiles & DOE and 7) commercial considerations. The selected Asset strategy and development scenarios is then used to provide inputs to the Long-Term Plan (LTP) working horizon who then serves as a reflection of vision and mission of MEPG.

- Long-Term Plan (LTP)

Long-Term Plan (LTP) translates the Asset strategy and ADP scenarios into an integrated long-term business plan, covering a ten-year outlook. It combines production, subsurface opportunities, development activities, operating assumptions, commercial considerations, manpower, and cost spending (CAPEX/OPEX) outlook. The LTP process and approval requirements shall follow the applicable Integrated Business Planning Guideline – E&P  (No. ID-G-BU-GG0-GUI-GN-00-3005).

This horizon is developed through the annual MEPI’s Integrated Business Planning cycle and updated in accordance with the applicable cycle set (Updated LTP) by E&P Planning division. For integrated planning purposes, LTP horizon consists of two distinct timelines:

  - 24-Month Planning Period. This timeline period provides a more detailed short to medium-term activities and major milestones in assets. Planning within this period timeline requires early cross-functional alignments activities such as 1) shutdown, 2) major maintenance, 3) projects, 4) drilling, 5) well activities, 6) major procurement, and 7) key contractual or commercial requirements.

  - Activities within this period are then reviewed for their timing, dependencies, constraint, interfaces, and alignment with the approved ADP plan. Relevant activities are then detailed progressively into the 12-month plan.

  - Outer-Years Period. This timeline period covers the remaining LTP planning horizon beyond the first 24 months. It also provides a longer-term view of Asset development, production, major spendings (CAPEX/OPEX), opportunities, and key business milestones.

    - Within this timeline period, the focus is more towards strategic direction, major assumptions, scenarios, and longer-term constraints. Relevant activities should be reviewed more thoroughly as they move closer to the 24-month planning period.

- 12-Month Plan (12M)

The 12-Month Plan (12M) is a rolling outlook of operationally impacting activities expected within the next 12 months. 12M provides early visibility of future activities and helped with the initial screening stage for short-term operational planning. 12M plan may include major operations, maintenance programs, planned shutdowns, projects, well activities, and other activities that may impact operational capacity or needing field execution.

Activities are reviewed at a high-level for priority, risk and mitigation plan, major constraint/blocker, interfaces, and resource requirements. After approval, 12M planned activities may progress into 90-Day Plan (90D) for further planning and prioritization.

- 90-Day Plan (90D)

The 90-Day Plan (90D) is a rolling outlook of activities anticipated within the next 90 days. It consolidates and prioritizes activities before detailed execution readiness validation. Activities are reviewed for priority, risk and mitigation plan, readiness, execution feasibility, resource and capacity requirements, SIMOPS, and cross-functional alignment.

Activities approved are Gate 1 during this stage become planned candidates and may proceed to detailed readiness validation for the 30-Day Plan. Gate 1 approval does not represent execution commitment.

- 30 Day plan (30D)

The 30-Day Plan (30D) is the execution commitment horizon. It is a rolling 30-day plan covering activities that have progressed through Gate 1 readiness review and are proposed for execution.

Activities are reviewed for the defined scope, manpower, materials, equipment, contracts, permits, HSE requirements, Management of Change (MOC), SIMOPS, resource availability, and other applicable execution constraints.

Activities that meet the applicable readiness requirements and receive Gate 2 approval are committed for execution and declared Frozen. Changes to committed activities shall follow the applicable break-in or change control process.

- 7 Day Plan/Plan Control (7D)

The 7-Day Plan is the detailed weekly execution control plan derived from the approved 30-Day Plan. It provides the activity sequencing and coordination required for day-to-day field execution. 7D planning process confirms final readiness, site coordination, manpower and resource deployment, SIMOPS, execution sequencing, and short-term constraints.

Gate 3 approval authorizes weekly execution of approved activities within the Frozen execution window. New scope, additional activities, or significant method changes shall not be introduced without the applicable break-in or change control process.

## Activity-Based Planning Processes

In addition to planning horizons described in Section 3.1, MEPG applies activity-based planning processes for specific types of work. These processes are not separate planning horizons, but provides the function-specific planning, assurance, and readiness requirements needed for activities to be integrated into the applicable planning horizons.

Activities from these processes shall be aligned with the Integrated Planning & Scheduling (P&S) process based on their timing, operational impact, stakeholders, constraint, and execution requirements.

- Maintenance Planning

This process covers the preparation, and coordination of preventive, corrective, and other maintenance activities required to maintain reliability, asset integrity, and operational performance of MEPG’s asset. The process includes: 1) work scope and work order preparation, 2) maintenance timing, 3) material and equipment requirements, 4) procurement and delivery status, 5) manpower and contractor requirements, and 6) operational constraints. Relevant maintenance activities shall be integrated into the applicable 12M, 90D, 30D, and 7D plans based on their criticality, readiness, and impact on operations.

- Project Planning

This process covers the development, planning, and execution preparation of applicable facility and development projects. This process shall be performed in accordance with the applicable Medco Project Excellence Process (MPEP) (No. MPEP-PM-GUI-03) where applicable. The project process shall establish the required project scope, schedule, technical readiness, cost, contracting and procurement requirements, resources, risks, and key project milestones.

Project activities and milestones that affect production, Operations, shutdown windows, SIMOPS, field resources, logistics, or other functions shall be included in the applicable planning horizons. This guideline governs the coordination of those interfaces and execution requirements without replacing the applicable MPEP project governance.

- Shutdown Planning

This process covers the preparation, and coordination of planned activities requiring facility shutdown, production reduction, or significant operational intervention. This process shall integrate the work requirements of Operations, Maintenance, Projects, Wells, and other relevant functions. The planning process shall consider: 1) shutdown scope, 2) production impact (through LPO), 3) activity sequencing, 4) SIMOPS, 5) manpower and contractors, materials, 6) equipment, logistics, and 7) any applicable commercial or external stakeholder requirements.

Major shutdown and resource requirements shall be identified in the applicable LTP and 12M timeline periods. Individual shutdown activities shall be progressively detailed, inspected for activities, and scheduled through the 90D, 30D, and 7D planning horizons as execution approaches.

- Early Operations Planning

This process covers Operations involvement during project development to ensure operability, reliability, maintainability, and operational requirements are considered before startup and handover. Early Operations involvement shall follow the applicable Operability Assurance (OA) requirements, including MPEP-PD-GUI-01 where applicable. Operations shall provide relevant input to operating requirements, maintenance needs, operational risks, and future readiness requirements during project development.

As the project approaches execution, startup, and handover, relevant Operations readiness activities shall be included in the applicable planning horizons. This includes, where applicable, manpower, operating procedures, training, maintenance requirements, materials, operational constraint, and startup support.

## Work Process/Flow

The Integrated Planning work process establishes a common flow for developing, reviewing, approving, and monitoring plans across the planning horizons described in Section 3.1. The process is iterative, allowing assumptions, priorities, constraints, and execution results to be reviewed and reflected in the relevant planning horizons.

Each planning horizon shall, at minimum, include the following process stages:

- Initiation and Input. The planning process is initiated based on the applicable planning cycle, business requirement, operational need, or previous planning horizon output. Relevant functions shall identify and submit the required activities, assumptions, opportunities, and planning information.

- Integration and Review. Planning inputs shall be consolidated and reviewed across relevant functions. The review shall consider priorities, risks, dependencies, constraints, resource requirements, readiness, and potential conflicts based on the level of detail required for the respective planning horizon.

- Decision and Approval. The integrated plan shall be reviewed and approved by the designated Plan Owner or approval authority for the respective planning horizons. Activities that do not meet the applicable requirements shall be revised, deferred, or returned for further development.

- Plan Hand-Off and Progression. Approved plans and relevant activities shall provide inputs to the next applicable planning horizon. The level of activity detail, readiness, and execution certainty shall progressively increase as activities move closer to execution.

- Performance Monitoring and Control. Plan progress, changes, constraints, and performance shall be monitored by the responsible planning and functional teams. Significant deviations or changes shall be reviewed and managed through the applicable plan administration, change control, or break-in process.

- Feedback and Adjustment. Planning and execution results, updated assumptions, and lessons learned shall be used to update the relevant planning horizon. Feedback may result in changes to activity timing, priorities, assumptions, or future to maintain alignment across planning horizons.

The planning flow is not strictly linear. Updated technical information, changes in business or operational priorities, emerging constraints, and execution results may require plans to be reviewed and adjusted at the relevant planning horizons.

Figure 2 – Multi-Horizon Planning Work Process (Horizon Overview) illustrates the planning flow across horizons, including each horizon's planning focus, review forum and cadence, designated chair, and approval authority. The figure also shows the progression of planning detail and certainty toward execution and the feedback of planning and execution results in the relevant planning cycles.

Detailed process requirements, planning criteria, approval authorities, roles and responsibilities, and monitoring and control requirements are described in the relevant sections of this guideline and applicable planning guidelines and procedures.

Figure 2  Multi horizons Planning Work Process

PEP

## Tools, System & References

Integrated Planning Processes in MEPG use various tools, systems, and corporate references to support its planning, data management, performance monitoring, activity coordination, and reporting across the planning horizons.

The tools and systems used may differ depending on the planning horizons, function, and type of activity. Where multiple systems are used, all stakeholders involved shall ensure that information remains consistent, current, and traceable across the relevant planning process.

The main tools, systems, and planning references used in MEPG’s Integrated Planning may include:

  - Integrated Business Planning (IBP) module in Medco BPM. Used to support business planning, budgeting, forecasting, and consolidation of planning information.

  - SAP. Used to support cost planning, cost allocation, budget monitoring, and tracking of expenditure against the applicable organizational and activity structure.

  - ARIS. Used to document and map applicable business processes, workflows, and process interfaces.

  - MCRS. Used to support applicable cost, resource, or management reporting requirements within the planning process.

  - SharePoint. Used as a common document and information-sharing platform for files, documents, and controlled planning information.

  - Well Delivery and Drilling Plan (WDDP). Provides the applicable planning framework and baseline planning reference for well delivery and drilling activities.

  - Medco Project Excellence Process (MPEP). Provides the applicable project governance, assurance, and planning requirements for projects across the relevant project lifecycle.

  - Production Forecasting Tools/Gas Processing Tools (GPT). Applicable forecasting tools and models may be used to support Short-Term Production Forecasting (STPF), production outlook, and planning assumptions.

  - Other Applicable Tools and Systems. Other function-specific tools, systems, templates, or planning references may be used where required to support the applicable planning and execution process.

# Roles, Approvals & Governance

## Plan Ownership and Approval

Each planning horizon, plan, program, or any grouped set of activities shall have defined planning ownership and approval authority appropriate to its scope and level of decision-making.

The Plan Owner is accountable for the planning outcome and progression of the plan within the applicable planning horizon. Plan ownership may reside with Subsurface, Asset Management, E&P Planning, Operations, or other designated functional leadership, depending on the nature and scope of the plan.

Supporting functions, including Projects, Well Operations, Engineering, Commercial, Relations, HSE, and other relevant functions, shall provide the required planning inputs and support the delivery of their respective activities.

In general, the Plan Owner is accountable for:

- planning performance and delivery of the agreed work program;

- key planning assumptions, premises, and material changes;

- resolution or escalation of conflicts, constraints, issues, and opportunities;

- milestone and plan status updates; and

- review of resource requirements and constraints applicable to the plan.

Each planning horizon shall establish the following governance roles, as applicable:

- Plan Owner. Accountable for the overall planning outcome, key planning decisions, and progression of the plan.

- Planning Process Focal Point. Coordinates the applicable planning cycle, planning inputs, review forum, hand-offs, and implementation of the planning process.

- Planning Administrator. Consolidates, updates, and maintains the required planning information and supports alignment of cross-functional activity schedules.

- Approval Authority. Reviews and authorizes the plan or planning decision within the assigned level of authority.

The Planning Process Focal Point facilitates the planning process but does not replace the accountability of the Plan Owner or individual activity owners. Similarly, the Planning Administrator supports plan development and control but remains dependent on timely and accurate inputs from the responsible functions and activity owners.

Approval shall be performed at the appropriate organizational level for each planning horizon. As plans progress toward execution, the approval focus shifts from technical and strategic direction to prioritization, execution commitment, and field execution control.

Approval of an integrated plan does not transfer accountability for individual activities. The respective activity or work owners remain accountable for the completeness, readiness, progress updates, and delivery of their assigned scope.

The general planning ownership, approval, focal point, and administration structure is summarized in Table 1 and aligned with the multi-horizon planning work process shown in Figure 2.

Table 1.  Plan Approval and Administration

| Planning Horizon |  | Coverage |  | Plan Ownership |  | Approval Authority |  | Planning Focal Point |  | Planning Admin. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Field Depletion Plan (FDP) |  | Field technical planning |  | SM Subsurface |  | Sr. VP Asset |  | As per FDP guidelines |  | As per FDP guidelines |  |  |
| Asset Dev. Plan (ADP) |  | Block / Asset Developments |  | Sr. VP Asset |  | CEO/COO |  | As per ADP guidelines |  | As per ADP guidelines |  |  |
| LTP (Outer Years) |  | 10-years+ business outlook |  | Asset Management |  | CEO/COO + Sr. VP Asset |  | Asset Management |  | E&P Planning |  |  |
| LTP (24-Month) |  | Major asset activities and milestones |  | Asset Management |  | CEO/COO + Sr. VP Asset |  | Asset Management |  | E&P Planning |  |  |
| 12-Month Plan (12M) |  | Operationally impacting activities |  | OIM/OM + relevant owners |  | VP Operations |  | P&S Team |  | Integrated Planner |  |  |
| 90-Day Plan (90D) |  | Prioritized planning candidates |  | OIM/OM and Superintendent |  | VP Operations (Gate 1) |  | P&S Team |  | Functional / Asset Planner |  |  |
| 30-Day Plan (30D) |  | Execution commitment |  | OIM/OM and Superintendent |  | OIM/OM (Gate 2) |  | P&S Team |  | Functional / Asset Planner |  |  |
| 7-Day Plan / Plan Control |  | Weekly field execution |  | Superintendent / SPV |  | Superintendent (Gate 3) |  | Functional Planner |  | Activity / Functional Planner |  |  |

## Roles and Responsibilities

Integrated Planning involves both governance roles and organizational roles. Section 4.1 defines the governance roles for each planning horizon. This section describes the main responsibilities of the organizational roles that support and execute Integrated Planning across the Asset.

The roles below may perform different governance functions depending on the planning horizon. In general, planning functions facilitate, coordinate, consolidate, and challenge the plan, while work owners and execution owners remain responsible for scope, readiness, updates, and delivery.

### Chief Executive Officer (CEO) & Chief Operating Officer (COO)

- Provide overall business direction for strategic and long-term planning.

- Review and approves the long-term planning outputs (ADP, FDP, LTP) within the assigned authority.

- Ensure major planning outcomes remain aligned with corporate strategic objectives.

- Provide direction on significant assumptions, constraints, and portfolio decisions requiring executive alignment.

### Senior Vice President (SVP)

- Provide overall direction for MEPG asset development and long-term planning.

- Review and approve applicable FDP, ADP, and LTP outputs within the assigned authority

- Ensure asset strategies, priorities, and major assumptions are reflected in the relevant planning horizon

- Resolve or escalate major cross-functional conflicts, constraints, and opportunities affecting asset objectives.

- Ensure relevant functions support the approved Asset plans.

- Holds accountability for their respective functions in delivering to the Plan Owner.

### Vice President of Operations (VP Ops)

- Provide overall direction and priorities for operational planning.

- Review operational priorities, major constraints, and cross-functional issues affecting the short-term planning horizons.

- Ensure operational planning remains aligned with Asset and business priorities.

- Resolve or escalate significant operational, production, resource, and capacity conflicts.

- Provide executive support for operational planning discipline and execution readiness

### Asset Management

- Ensure that approved plan changes are thoroughly assessed with a disciplined and rigorous approach.

- Monitor Key Performance Indicators (KPIs) for planning and implement improvements where necessary.

- Coordinate with all functions to ensure their support and alignment with the planned objectives.

- Ensure that engineering studies and execution plans are structured and managed in accordance with Integrated Planning processes.

- Facilitate input from various groups into the plan and assist in resolving conflicts among stakeholders.

### E&P Planning

- Coordinate the applicable LTP and Integrated Business Planning processes.

- Consolidate planning information and planning packages required for the LTP cycle.

- Coordinate planning assumptions, reviews, updates, and hand-offs within the LTP process.

- Support the alignment of Asset plans across the E&P planning process.

- Maintain the applicable long-term planning outputs and planning information.

### Operations Planning and Activities Assurance (OPAA)

- Coordinate planning cycle, inputs, review forums, and hand-offs for the 12M, 90D, and 30D horizon.

- Consolidate and maintain operational planning information, priorities, readiness inputs, and scheduling details.

- Review planning inputs for completeness, dependencies, constraints, conflicts, and readiness requirements.

- Identify and escalate planning conflicts, capacity issues, and significant deviations to the relevant Plan Owner or approval authority.

- Support the implementation of planning standards, templates, and planning records for operational planning.

- Maintain applicable operational planning processes, templates, records, and planning information.

- Monitor and communicate operational planning performance indicators and support process improvement.

### Plan Owners

- Hold accountability for the planning process, progression, and outcome of their respective plan, program, or grouped activities.

- Review and incorporate salient information from external sources that may influence planning decisions.

### Managers (Field, Drilling, Project, Exploration, Engineering, Support Functions)

- Ensure approved plan changes are rigorously assessed to maintain alignment with objectives, priorities, and constraints.

- Track applicable planning KPIs and implement improvements based on identified trends and insights.

- Review and approve or reject plan changes within the 30-day Frozen plan, in accordance with the applicable approval authority and change control or break-in process.

- Ensure that engineering studies and functional activities are structured and managed in accordance with the Integrated Planning processes to enhance coordination and efficiency.

- For Projects, ensure major initiatives are structured and managed in compliance with Integrated Planning processes and applicable corporate project governance requirements.

### Installation Manager / Superintendent

- Lead activity and resource coordination for planning purposes within their respective operational areas.

- Review field priorities, execution readiness, SIMOPS (Simultaneous Operations), capacity, and execution constraints.

- Lead activity and resource planning for the applicable short-term operational planning horizons.

- Ensure the required operational resources and field inputs are available to support planning and execution.

- Maintain planning and execution discipline and minimize avoidable plan changes.

- Implement approved plans and ensure activities remain aligned with agreed operational priorities and objectives.

- Resolve or escalate field execution conflicts and emerging constraints.

### Other Department / Team Leaders

Provide input and support for prioritization and conflict resolution during plan development, including all relevant business support activities.

### Responsible Person / Job Owner

The Responsible Person / Job Owner is responsible for the preparation, readiness, and delivery of an individual activity within the approved plan. Unlike the Plan Owner, this role is responsible for the assigned activity rather than the overall planning outcome or planning horizon.

- Maintain accurate and up-to-date activity information in the applicable planning tools, BPM Work Orders, and planning inputs, including scope, schedule, resource requirements, and activity revisions.

- Define and prepare the assigned activity in accordance with applicable planning and readiness requirements.

- Identify and communicate activity requirements, constraints, risks, progress, and changes to the relevant planning stakeholders.

- Provide timely progress and readiness updates throughout the applicable planning horizon.

- Provide justifications to Planners when requesting approval from the Functions/Operations Manager for any changes during the 30-day frozen period.

- Deliver the assigned activity in accordance with the approved plan and escalate significant deviations or constraints.

# Governance Model

The governance model for integrated planning incorporates feedback loops to ensure that information and decisions flow effectively both top-down (from long-range to operational planning) and bottom-up. This model facilitates information sharing across planning horizons

Each planning horizon is supported by an applicable planning meeting or review forum. These meetings provide the mechanism to review planning inputs, discuss priorities and constraints, make the applicable planning decisions, and monitor plan progression.

The general meeting cadence, key participants, planning inputs, and expected outputs for each planning horizon are summarized in Table 2. The operational governance sequence of 12M, 90D, 30D, and 7D is consistent with the current Integrated Corridor Operation Planning Procedure(No. ID-G-BU-GG0-PRO-GN-00-3007, 1st issuance).

Table X.  Overview of Integrated Planning Meeting Cadence

| Planning Horizon | Meeting Cadence |  |  | Key Participants | Main Inputs |  | Expected Outputs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Field Depletion Plan (FDP) | Annual Cycle |  |  | Plan owner, Focal Point, Relevant Functions | Technical basis, opportunities, scenarios |  | Approved FDP/ADP planning output |  |
| Asset Dev. Plan (ADP) |  |  |  |  |  |  |  |  |
| LTP (Outer Years) | Bi-Annual Cycle |  |  | E&P Planning, AM, relevant functions | ADP, Production, Cost, Assumptions |  | Long-term outlook |  |
| LTP (24-Month) |  |  |  |  | Activities, milestones, constraints |  | 24M Activity Outlook |  |
| 12-Month Plan (12M) | Quarterly |  |  | VP Ops, OIM/OM, OPAA, relevant functions | Activities, Risk, Constraint, Capacity |  | 12M Plan baseline |  |
| 90-Day Plan (90D) | Monthly |  |  | VP Ops, OIM/OM, OPAA, planners | Priorities, Readiness, Capacity, SIMOPS |  | Gate 1 – 90D Plan |  |
| 30-Day Plan (30D) | Monthly |  |  | OIM/OM, Superintendent, planners | Readiness, Resources, HSE, MOC, SIMOPS |  | Gate 2 – Frozen Plan |  |
| 7-Day Plan / Plan Control | Weekly |  |  | Superintendent, planners, execution functions | Final readiness, sequencing, constraint |  | Gate 3 – Weekly Plan |  |

## Meeting Term of Reference

Efficient and focused communication across the integrated planning processes requires that all regularly scheduled meetings be guided by a clear Terms of Reference (TOR). The TORs for each planning horizon are outlined in Appendix A – BU Life Planning and Appendix B – Meeting Term of Reference.

# Criteria of Activities Inclusion into Plan

## Activities shall be included in the Integrated Planning process based on the level of visibility required within each planning horizon. The level of inclusion may vary depending on the activity type, operational or production impact, resource requirements, business materiality, cross-functional stakeholders, and other applicable planning considerations.

## Inclusion Criteria Matrix

Not every activity requires the same level of visibility across all planning horizons. This guideline provides general criteria for determining which activities should be included in each horizon, considering the following factors:

- Activity Type. Activities are identified as either Function-specific or Integrated, depending on the level of cross-functional coordination required.

- Planning Horizon. Activity inclusion is assessed across the applicable planning horizons, from LTP through short-term operational planning and execution control.

- Inclusion Criteria. Activities may be included based on defined conditions or thresholds, such as operational or production impact, workforce or resource requirements, financial materiality, regulatory or approval requirements, and other activity-specific considerations.

- Schedule Visualization Granularity (level-of-detail). The level of schedule visualization generally increases as activities progress toward execution.

Where “ALL” is stated in the matrix, all activities within the applicable category shall be included. Where a specific threshold or condition is stated, the activity shall be included when the applicable criterion is met.

The criteria represent the minimum level of visibility required within the Integrated Planning process. Functions may maintain more detailed plans and schedules within their respective planning processes and systems. Activities below the stated criteria may also be included where required due to risk, operational impact, cross-functional dependency, resource constraints, or management direction.

A typical list of activities and their applicable inclusion criteria for each planning horizon is summarized in Appendix C – Planning Activity Inclusion Criteria.

## Schedule Levels (AACE)

Efficient and focused communication across the integrated planning processes requires that all regularly

These horizons generally align with the Numeric Schedule Levels as defined by International Recommended Practice No. 37R-06, as follows:

- Long-Term Plan (LTP). Corresponds to a Level 1 high-level schedule, focusing on key milestones and summary activities.

- 24-Month Plan. Provides a breakdown of the long-term plan and highlights the integration of major works and milestones across functions.

- 12-Month Plan (12M). Provides a higher level of operational visibility and supports early screening of activities that may affect near-term execution.

- 90-Day Plan (90D). Represents the first level of detailed operational screening and prioritization for activities moving toward execution.

- 30-Day Plan (30D). Represents execution commitment and detailed readiness validation for activities within the Frozen Plan.

- 7-Day Plan (7D) / Plan Control. Comprises detailed weekly execution planning and work-package level control for field execution.

The specific level of schedule details may vary depending on the type and complexity of the activity. Function/activity-specific schedules may contain more detail than the integrated plan while remaining aligned with the applicable Integrated Planning horizon.

# Managing the Plans

- The management of integrated plans requires consistent processes for developing, reviewing, updating, and controlling activities across the applicable planning horizons. As activities progress from more strategic, longer-term planning toward tactical and executional, the level of detail, certainty, readiness, and control shall progressively increase.

- Plans shall be managed to maintain alignment across functions and planning horizons, identify and resolve constraints and conflicts, confirm activity readiness, and control changes to approved plans. The requirements in this section apply according to the purpose and level of detail of each planning horizon.

## Acceptance/Input Criteria

- Maintaining consistent acceptance and input criteria is crucial for ensuring the compatibility and coordination of activities from various sources into a unified integrated plan. This approach facilitates the identification of potential conflicts, such as skilled labor availability, rig constraints, and capital limitations, while also uncovering synergies and optimizing the sequencing of activities.

- Activities shall meet the applicable inclusion criteria for the relevant planning horizon as defined in Appendix C – Planning Activity Inclusion Criteria. The information required to support planning, integration, and review shall be progressively developed as activities move toward execution. Typical input criteria for each planning horizon are detailed in Appendix D.

## 12 Month Plan (12M)

12M Plan provides a rolling view of operationally impacting activities expected within the next twelve months. It serves as the transition between the LTP and detailed operational planning by consolidating relevant activities from the approved LTP and other applicable functional or operational inputs.

12M Plan is intended for early screening, integration, and coordination. Activities included in the plan are not yet committed for execution. The plan provides sufficient visibility to identify potential priorities, dependencies, interfaces, risks, constraints, and resource requirements before activities progress into the 90D Plan.

Activities proposed for inclusion in the 12M Plan shall, as applicable, include:

- activity identification and description;

- responsible function and activity owner;

- indicative timing and major milestones;

- preliminary scope and duration;

- major resource and capacity requirements;

- key dependencies and interfaces;

- known risks and constraints;

- potential operational, production, HSE, SIMOPS, or commercial impacts; and

- other information required to support cross-functional screening and integration.

12M plan shall be periodically reviewed and updated to reflect changes in priorities, assumptions, activity timing, constraints, and the latest available information. Activities approaching the operational planning window shall be progressively developed to the level of information and readiness required for consideration in the 90-Day Plan.

Progression from the 12M Plan into the 90D Plan shall not constitute execution commitment. Activities shall remain subject to the applicable prioritization, readiness, and approval requirements before progressing toward the 30D Frozen Plan and subsequent execution.

## 12 Month Plan (12M)

The first 30 days of an approved plan, issued monthly, are considered "frozen." This means that all work activities within this period are fully defined, with all preparatory work, equipment, and resources confirmed to be available for execution within the specified timeframe. If specific gate requirements are not met 30 days before the planned work commencement date, the job will be removed from the plan.

Activities in the 30 days plan should typically include detail for the following:

- Activity number.

- Activity description.

- Main Work SAP or Cost Centre.

- Task lead/ responsible person for field work.

- Man-Hour Estimates per operation and per resource.

- Operation Calendar (Day-Night shift, Day and Night, 24 hour etc.).

- Required Start and End Date.

- Optimistic, Expected and Pessimistic Duration.

- Functional Location at Order Level or Operation Level.

- Number of personnel to be mobilized to field for the task broken down by company name (COPI and contractors), including supplier and specialist support.

- Number of expected field operations personnel support.

- Contractor schedule is ready.

- List of specific tools, equipment required from Operations (crane, scaffolds, boat, vehicles, etc), consumables and applicable locations lists.

- Any other specific requirement or information that Operations or other departments need to know.

Criteria for other functions (non-field operations) may include factors such as required work manhours, availability of specialists, service contract readiness, defined start and end dates, and the anticipated duration of the activities.

## Gate Review Criteria

Sheltering losses resulting from inefficient planning is achieved by ensuring high-quality planning that supports thorough analysis and integration. Two key gate reviews are implemented:

- Sufficiency of Information Review: This step ensures that adequate and accurate information is entered into the plan. If the information provided is insufficient, planners must obtain additional details from the job owner. Typical information required is outlined in Appendix D.

- Readiness Gate Review: This review assesses whether an activity is prepared for integration into the execution phase. It applies specifically to activities scheduled within the 30- and 90-day planning horizons. Activities failing to meet readiness criteria will not proceed to execution.

### Gate Requirement for 90 Day plan

The following are the gate requirement for the activities to be included in the 90 Day Operations plan:

- Funding in the Medco LTP and annual WP&B.

- Obtain consent to proceed from Partners and internal Medco.

- Obtain permitting requirement.

- Engineering design sufficiently matured.

- Execution contract is available.

- Materials readiness.

- Simultaneous Operations to avoid site conflict.

- HSE Mitigation in place.

### Gate Requirement for 30 Day plan

The following are the gate requirements for activities included in the 30-Day Operations Plan:

- all necessary materials and tools have been delivered to the site and confirmed to meet the required specifications,

- the work pack, including procedures, drawings, and other documentation, is complete and has been reviewed or approved,

- internal support resources have been confirmed and meet all HSE requirements for mobilization,

- the specialist vendor has been contacted and has provided a commitment, including personnel details, schedule, and mobilization date,

- materials and positions required for stakeholder and government engagement have been confirmed and agreed upon.

## Managing Constraints

When developing plans, especially at the 30/90-Day Plan level, several constraints must be considered. These constraints are typically classified into two categories: static and dynamic. Static Constraints tend to remain relatively unchanged over time and include factors such as the number of beds, life boat seat availability, regulatory permits, personnel access to specific areas, ongoing SIMOPS (Simultaneous Operations) restrictions, and limitations set by design or building codes.

Dynamic Constraints are subject to frequent changes and require a more responsive management process. Examples include weather conditions, seasonal access, availability of specialist services and personnel, and dynamic SIMOPS conditions (e.g., ongoing work, equipment downtime, etc.).

When developing plans, it is essential that all identified constraints are understood, communicated, and updated regularly. The following are typical constraints that should be considered as part of the P&S process.

### Permitting and Other Stakeholders Approvals

The readiness of a work activity should consider all necessary clearances, permits, and approvals from relevant stakeholders. This includes budget and AFE approvals from government/SKKMigas, Partners, and internal Medco, as well as permits from agencies such as MIGAS, Seacomm, Aircomm, and local governments.

### Resources Planning & Manpower Histogram

Resources, including headcount and associated costs, are tied to planned activities. Headcount resources should be validated and leveled according to numbers, competencies, and timing (e.g., manpower histogram). Hiring plans should also be considered as a potential constraint to ensure that the required skills are available when needed.

Cost constraints should be validated against the budgeted items in the LTP and the approved AFEs.

### Personnel on Board and Bedding Capacity

One of the primary constraints to consider when preparing the 30/90-Day Field Plan is the Personnel on Board (POB) capacity at field locations. The total manpower should not exceed the pre-defined maximum POB.

### Crew Change Schedule & Logistics

Field Asset Operations provide regular transportation for personnel mobilization and demobilization. Mobilization outside of these scheduled times may require additional approvals, such as from the area Superintendent.

Material transportation from Jakarta to the field is arranged regularly by the Material Management group. Contractors should also consider transportation arrangements for goods and materials when developing the plan.

### General Contractors Capacity

The availability of 3rd party resources should be confirmed before they are included in the 30/90-Day Plan. The contractor's schedule must reflect their readiness to execute the work.

### Material Readiness and Supply Chain

Materials and contracts required for any task should be identified early, considering the procurement/contracting process, delivery times, and transportation to the field. Task leads are responsible for identifying the required materials, quantities, and specifications, and passing this information to the planners to create requisitions in the system if the materials are not available in stock.

If materials are available in stock, maintenance planners should make reservations and communicate with the Materials Management team to ensure the materials are available when needed at the site.

Planners will facilitate communication with Procurement and Materials Management through the contract administrator based in the Jakarta Office to expedite the procurement process, materials delivery, and report on materials readiness status.

Activities included in the 90-Day Plan must have confirmed materials delivery prior to the scheduled execution. Activities listed in the 30-Day Plan should have all materials delivered to the site or be en route. Any exceptions require approval from the OIM or Field Manager.

### Work Pack

The 90-Day Plan includes all activities that meet the 'entry criteria' within the 90-day window. Activities listed on the 90-Day Plan (but not yet on the 30-Day Plan) have at least 30 days to develop the work pack before being included in the 30-Day Plan.

### Operations and Maintenance Activities

BPM identifies all plant and equipment that require maintenance across all assets and specifies when and by whom the work will be carried out. This includes Planned Maintenance Routines (PM), which are recurring activities performed at a set frequency, and Corrective Maintenance Routines (CM), which are created to address additional work arising from inspections, breakdowns, or repairs to plant and equipment.

Although BPM identifies when Preventive Maintenance activities are due, certain activities may need to be included in the Integrated Plan to raise awareness among the maintenance crew and field supervisors, ensuring alignment and optimizing resources.

## Risk Assessment

The characterization of risks associated with planned activities can facilitate prioritization. Risks should be evaluated in terms of potential impacts on safety, the environment, execution, production, and other relevant areas. Risk assessment and communication should be integrated throughout the planning process, with particular emphasis at the 30/90 Day field execution planning stage.

### Strategic Planning Horizon

At the strategic level, risk assessments will be conducted based on their potential long-term impact on MEPG. Business prioritization at this level may encompass safety, environmental impact, production, and high-level SIMOPS activities. Specifically, completion risk for Major Projects can be characterized by developing risked schedules using a probabilistic Contingency Breakdown Report (CBR) methodology. This methodology may include calculating P10, P50, and P90 schedule and cost estimates.

### Tactical Planning Horizon

At the Tactical Level, risk evaluations, similar to those at the Strategic Horizon, will address high-level risks but with a focus on individual program or asset risks. For instance, key risks to Major Projects will be identified in terms of both cost and schedule impacts. For operating assets, potential production downtime due to shutdown windows will be considered, and significant upcoming maintenance programs will be highlighted.

### Operational Planning Horizon

At the operational level, detailed risk assessments are conducted for planned activities, considering the inherent hazards of each activity, project, or operation.

During the design and planning stages, these assessments include analyses such as Hazard Identification (HAZID), Hazard and Operability (HAZOP) studies, SIMOPS analysis, Safety Integrity Level (SIL) evaluations, Quantitative Risk Assessment (QRA)/CBR, and other design risk assessments. As activities transition to field execution, the focus shifts to safety and execution readiness, using tools such as Pre-Job Hazard Analyses (PJHA) and toolbox talks. The MEPG risk matrix (Appendix E) may be used as applicable.

### Contingency Planning

The outcomes of risk assessments will guide the evaluation, development, and planning of contingency measures. Key features of contingency management are as follows:

- Contingency plans are developed by cross-functional teams representing relevant areas of expertise.

- The allocation of resources and the approval process are commensurate with the assessed level of risk.

- Contingencies for tasks and equipment, including necessary materials, resources, and logistics, are integrated into the project plan and schedule.

- Schedule contingencies incorporate a defined recovery strategy.

Contingency planning may utilize a formalized methodology, such as the QRA/CBR employed by Projects, or be addressed as a standard component of regular planning meetings.

## Conflict Resolution and Plan Prioritization

When activities are added to the integrated plan, potential conflicts may arise at various stages. Prioritization of activities should be guided by standard criteria, with the primary objectives being:

- Ensuring adherence to safety and environmental standards.

- Maximizing value creation for the BU.

- Maintaining alignment with the goals and objectives of the BU.

At different planning horizons, prioritization may take various forms:

### Strategic Planning Horizon

Prioritization is typically based on Net Present Value (NPV) or risk assessments, with a focus on alignment with BU goals and objectives.

### Tactical Planning Horizon

Similar to the Strategic Horizon, prioritization in the Tactical Horizon also considers NPV and risk but is more specifically tailored to individual projects, programs, or activities

### Operational Planning Horizon

At the Operational Horizon, prioritization and conflict resolution are centered on addressing immediate risks. Recommended criteria for prioritizing activities and resolving conflicts include, but are not limited to:

- Health, Safety, Environment

- Asset Integrity

- Production Loss

- Human Factor and Working Environment (i.e. noise, morale, physical conditions, etc.)

- Execution Opportunity Costs / Synergy Savings

- Adequate planning / preparation time and resource allocation

- Consideration of fatigue and overall activity impact.

### Escalation Path

Bahas mengenai:

What to do on conflict; what if it doesn’t align with the planned horizon; (optional) resolution time)

## Opportunity Identification

New, bahas apa itu opportunity, type by impact.. subsection:

  - Types of opportunity (divided by cost, time, scope, quality, etc can add more)

  - Cara melakukan assessment opportunity (OPZBB, process improvement, kaizen, etc)

  - Step melakukan integrasi opportunity ke existing plan:

    - What to do (assess identifikasi, impact,, risk, mitigation plan)

    - Follow decision making framework (well defined problem, decision, and managed risks)

    - Where to align/approve)

## Output/Deliverables per Horizon

[NEW] A deliverables table per horizon (ADP/ FDP / LTP / 30-90 / 7-day), covering:

a) output;

b) format;

c) owner;

d) cadence.

## Administering the Plan

### Documentation

Planning and scheduling information should be documented to track progress and capture metric data for trend analysis. For Operational Horizon, each function planner is responsible for maintaining and storing detailed planning files, while Tactical and Strategic Horizons, summary plans are compiled and stored in a centralized SharePoint repository to ensure accessibility for a broader audience.

### Data and Information Management

Effective data management enables asset leadership and data management personnel to define the requirements for data access and organization. This ensures the asset can effectively track and meet its planning and scheduling goals. Data management follows MEPG procedures, as overseen by the IT department. These procedures include:

- Storage and repository

- Governance and control

- Quality and completeness

- User access

### Plan Communication and Visualization

The plans should be communicated effectively to relevant employees and contractors to ensure that all individuals clearly understand the objectives and their personal contributions toward achieving the planned goals. Visualization of the plans at each horizon should enable a quick and comprehensive understanding of the schedules, milestones, and overall strategy.

### Version Control Rule & Source of Truth

The plans should be communicated effectively to relevant employees and contractors to ensure that all individuals clearly understand the objectives and their personal contributions toward achieving the planned goals. Visualization of the plans at each horizon should enable a quick and comprehensive understanding of the schedules, milestones, and overall strategy.

## Change Control for Operational Planning Horizon

Changes to the approved 30-day plan should be minimized. However, if a change is deemed necessary, it must follow the appropriate authorization process.

For field operation activities, changes that do not affect constraints (e.g., bed capacity, SIMOPS, cost, HSE risks, or other issues) can be approved by the Plan Owner. If the proposed change impacts constraints, it must be escalated to the OIM for review, with final approval at the discretion of the Field Manager (FM).

When evaluating changes that impact constraints, the FM should consider factors such as the criticality of the work, resource availability, logistics, POB capacity, and other relevant considerations.

A ‘change’ to the approved 30-Day Plan is defined as any of the following:

- Adding work to the approved plan, particularly if it requires additional resources or support. Depending on the nature and criticality of the work, email confirmation from the FM or OIM may suffice.

- Delays to tasks within the approved plan that could impact constraints or other tasks in the plan.

- Inclusion of projects or activities that require additional budget.

- Other additions, cancellations, or delays deemed substantial enough to require authorization.

When a change to the 30-Day Plan is necessary, the Plan Change Control Procedure outlined in Appendix F should be utilized.

ADD BREAKIN MANAGEMENT

1) [NEW] Establish a break-in process from the planner's side;

2) [NEW] Standardize the readiness checklist handed from project planner to operation planner;

3) [NEW] Standardize the full break-in process across all sources (operations & non-operations);

4) [DECIDE] Confirm with Kang Oi / Mas Fikri whether a break-in template already exists to adapt (Kang Oi to send one).

# Assessing Performance

## Debriefing and After Action Reviews (AAR)

The AAR is a valuable tool for learning from both successes and failures. Its primary objective is to engage participants involved in the activity to review variances from the plan. This collaborative approach allows leaders to leverage group dynamics and reach a shared understanding of key lessons learned.

The AAR should focus on identifying lessons that can significantly enhance performance. These insights, whether they are best practices or opportunities for improvement, should be integrated into the overall strategy to drive continual progress.

The benefits of the AAR approach:

- Provides valuable insights for others involved in similar activities, helping to avoid repetitive mistakes and unnecessary relearning.

- Facilitates a common understanding of actual events and variances from the original plan.

- Identifies opportunities for improvement and establishes actionable steps for progress.

- Ultimately aims to improve the way we conduct our business and achieve better outcomes.

Further details about the AAR, including its processes, structure, and application, can be found in Appendix G – Conducting After Action Review.

## Planning Compliance

Assessing compliance with the BU planning processes requires multilateral communication between planners, plan users, and plan owners. Compliance is not just about whether processes are being followed, but also about their understanding, value, and their role in facilitating continuous improvement. If processes are not being adhered to, it may indicate that the processes themselves need to be rectified.

## Peer Review

Peer reviews enable independent observers to evaluate planned activities and identify potential flaws and opportunities for improvement.

Documentation pertaining to field operations peer reviews is available on the respective asset's Field Operations Planning site. In general, peer reviews should be conducted for field operations involving:

- Shutdown plans that cause a reduction of at least 50% in the normal production rate.

- Activities classified as having high or significant safety risks.

For projects executed under Corporate Authorization, peer reviews are an integral component of the MPEP and are documented within the corresponding project records.

## Business Performance Review

Robust management systems are designed to drive continuous improvement in organizational effectiveness and efficiency. Three fundamental components contribute significantly to sustained business performance improvement:

- Governance: The framework that governs and sustains business performance reviews over time.

- Documentation: The systematic collection of records that define the underlying data, analyses, and visualizations.

- Metrics:  The established standards used to measure business performance. Performance reviews for P&S typically consider the following metrics:

- Performance in terms of milestones, production, and costs across various timeframes (e.g., plan-on-plan, gate-on-gate, year-on-year).

- KPIs, including man-hour, cost, and schedule efficiency, and plan attainment.

Clear accountabilities for plan ownership, review, and business performance have been established within the business processes, with a focus on the Tactical and Strategic Horizons.

## Key Performance Indicator (KPI)

KPIs are metrics that are visible across the organization and are used to highlight and drive performance within P&S. These key metrics are documented in the business process maps associated with each horizon and in the overall Management Control and Reporting System (MCRS).

At the Operational Horizon, which focuses on the short term, metrics related to attainment, stability, and efficiency are applied. In contrast, longer-term KPIs primarily assess compliance with the planning process. Certain functions, such as Projects, maintain supplementary statistics for internal purposes, including man-hour, cost, and schedule efficiency; however, these are not comprehensively detailed within the BU procedure.

The following secondary performance measures may be considered for further development into defined KPIs:

- Plan Utilization: This metric measures the extent to which planned activities on baselined work align with the resources available for their completion.

- Plan Stability: This metric quantifies the number of interventions or changes made to the approved plan during the defined planning period.

- Work Efficiency: This metric compares the amount of planned work performed (both scheduled and unscheduled) to the resources available for performing that work.

- Disturbance/Delay: This metric tracks non-productive time associated with activity execution, categorized using standardized reporting codes, such as delays due to material availability, weather conditions, or permit approvals.

Examples of specific KPI’s calculated 30 day plan are shown below:

### Schedule Attainment

Schedule attainment is a measure of adherence to the planned schedule over a given time period (e.g., a month). Higher attainment percentages indicate improved schedule performance. It is determined by calculating the percentage of:

Actual % Progress of the Month

Schedule Attainment (%) = ------------------------------------------------------  x SF

Planned % Progress of the Month

Notes :

SF = Schedule Shift Factor is determined based on schedule shifts (delays) and activity duration:

- 1 – applied when the schedule is shifted (delayed) by 14 days or less

- 0.95 – applied when the schedule is shifted (delayed) by more than 14 days or when the activity duration is 25% longer than originally planned.

- 0.90 – for activities on the critical path, when the schedule is shifted (delayed) by more than 14 days, or the activity duration is 25% longer.

If an activity has started but is subsequently postponed, the SF is omitted. Overall schedule attainment is calculated by weighting individual schedule attainment based on the duration of work performed on each activity during the month.

### SPI (Schedule Performance Indicator)

SPI indicates the project’s progress performance

Actual % of Cumulative Progress

SPI (%) = --------------------------------------------------

Planned % Cumulative Progress

### Plan Break-in

This metric evaluates the organization's proficiency in developing and reviewing plans prior to their formal approval and distribution. Effective planning should result in a minimal number of changes post-approval. Plan break-ins represent additions to the established 30-day plan baseline. It is measured as the percentage of:

Total Number of Additional Activities

Plan Break-in (%) = --------------------------------------------------------------------------------- x 100%

Total Number of planned Activities in the approved 30D Plan

### Plan Deletion

A plan deletion refers to the cancellation of an approved 30-day plan baseline. It is measured as the percentage of:

Total Number of Activities of deleted tasks

Plan Deletion (%) = ---------------------------------------------------------------------  x 100%

Total Number of planned in the approved 30 D Plan

## Benchmarking Strategy

The purpose of the MEPG P&S benchmarking strategy is to support the identification of areas for improvement and to ensure robust planning processes. This strategy addresses the following key areas:

- Shutdown planning – Shutdown performance is benchmarked at the field Operational horizon and documented on the respective asset's Field Operations Planning SharePoint site. Benchmarking comparisons may encompass both operated and non-operated assets within MEPG.

- Projects –  For projects executed under the Corporate Authorization framework, benchmarking is an integral part of the assurance process (e.g., MPEP). The results of benchmarking evaluations are retained within the project documentation. Historical project performance metrics are maintained by the function to facilitate future benchmarking activities.

Benchmarking studies may, where appropriate, incorporate performance data from competitors and other relevant industries, such as nuclear, mining, and finance. In particular, for major projects and other critical activities, external data sources can serve as a key element of the assurance process.

SPECIFy SCOPE, PEERS TO REVIEW, AND FREQUENCY OF REVIEW (OPTIONAL)

## Reporting Cadence & Ownership

Create reporting matrix convering:

    - Metric

    - Owner

    - Cadence

    - Forum

# Continuous Improvement

## Program Structure

The implementation of a structured continuous improvement program provides direction for addressing performance gaps and serves as the basis for defining system goals and priorities. The Steering Committee holds accountability for establishing a culture of continuous improvement within P&S, a responsibility formalized through the issuance of a structured improvement plan. The Steering Committee monitors the dissemination of this desired P&S culture throughout the organization, ensuring that corrective actions are implemented to sustain and manage performance effectively.

Refer to Section 2.5 for a detailed description of the Steering Committee's Roles and Responsibilities.

## Review Cadence

To maintain the relevance of business processes and to assess performance against established standards, periodic reviews are conducted as follows:

## Ownership Model

To maintain the relevance of business processes and to assess performance against established standards, periodic reviews are conducted as follows:

# Future State – Dynamic Plan Management

The ideal future state of planning is one where decision-makers have enhanced visibility into their business and are empowered to make informed, efficient decisions. This vision moves beyond traditional “top-down” or “bottom-up” planning processes, fostering greater interaction between decision-makers and the analysts who provide critical data.

Dynamic Planning enables decision-makers to pose questions about the plan without the need for repeating, resubmitting, or redoing work. Adjustments to sensitivities, such as price, foreign exchange, or inflation, can be applied seamlessly without requiring involvement from the entire organization.

Integrated Planning centralizes planning data by aligning budget, economic, and financial planning processes. By eliminating conflicting data sources, this approach ensures that the resulting information and analyses are accessible at all organizational levels. The outcome is a more efficient and well-informed organization that can respond effectively to changing circumstances.

# Planning Process Review and Adjustment

## Continuous Improvement

The implementation of a structured continuous improvement program provides direction for addressing performance gaps and serves as the basis for defining system goals and priorities. The Steering Committee holds accountability for establishing a culture of continuous improvement within P&S, a responsibility formalized through the issuance of a structured improvement plan. The Steering Committee monitors the dissemination of this desired P&S culture throughout the organization, ensuring that corrective actions are implemented to sustain and manage performance effectively.

Refer to Section 2.5 for a detailed description of the Steering Committee's Roles and Responsibilities.

## Reviews and Assessments

To maintain the relevance of business processes and to assess performance against established standards, periodic reviews are conducted as follows:

Table 2.  P&S system Reviews and Assessments

| Review / Assessment | Frequency | Accountability | Comments |
| --- | --- | --- | --- |
| Medco E&P Grissik Ltd (MEPG) Integrated Planning and Scheduling Guideline | Needed, Q3 | BU P&S Lead | Doc. ID-G-BU-GG0-PRO-GN-00-0053, reissued |
| Business Process Maps | Annually, Q3 | Process Owner | Current version in ARIS, update and revise validity period |
| Local and Corporate OE reviews | Defined by BU OE lead | BU P&S Lead | Structure, timing, and actions coordinated with BU OE Lead |

In addition to scheduled assessments, business processes may be revised at any time in response to SIP action close-outs, AARs, feedback received from the planning community, audit findings, or other ad hoc reviews. The process owner is accountable for ensuring the incorporation and appropriate communication of these revisions.

# Alignment with Operating Cost Management

The planning process integrates Operating Cost Management principles, focusing on cost forecasting, tracking, and controls to effectively:

- Manage opportunities for acceleration, deferral, deletion, addition, and cost minimization.

- Assess the impact of plan changes on cost forecasting and budgets.

- Facilitate the use of cost estimating data with progressively higher levels of detail and accuracy as the execution timeframe approaches.

Further details are outlined in the Terms of Reference (TOR) for the Strategic and Tactical plan meetings (Appendix B). As shown in the Relationship Map, the Annual LTP and Forecasting Planning Calendar serve as triggers for adjusting the timing within the Tactical and Strategic planning horizons. The annual planning cycle is reviewed collaboratively by (but not limited to):

- Asset Management Team.

- E&P Planning Team.

- Business Analysis Team.

Key dates within the planning systems at both the Strategic and Tactical levels should align consistently with the cost phasing data provided during the LTP and forecasting cycles.

Accountability for the quality of planning and forecasting—both in terms of scheduling and costs—rests with the Plan Owner(s). In an asset-based organization, Plan Owners are typically part of the Asset or Operations Management teams. However, exceptions may occur where other individuals are designated as Plan Owners. Responsibility for producing planning dates and associated cost forecasts generally lies with the functional groups that supply the data to the Plan Owner. At both the Tactical and Strategic horizons, all Plan Owners should be clearly identified.

# Future State – Dynamic Plan Management

The ideal future state of planning is one where decision-makers have enhanced visibility into their business and are empowered to make informed, efficient decisions. This vision moves beyond traditional “top-down” or “bottom-up” planning processes, fostering greater interaction between decision-makers and the analysts who provide critical data.

Dynamic Planning enables decision-makers to pose questions about the plan without the need for repeating, resubmitting, or redoing work. Adjustments to sensitivities, such as price, foreign exchange, or inflation, can be applied seamlessly without requiring involvement from the entire organization.

Integrated Planning centralizes planning data by aligning budget, economic, and financial planning processes. By eliminating conflicting data sources, this approach ensures that the resulting information and analyses are accessible at all organizational levels. The outcome is a more efficient and well-informed organization that can respond effectively to changing circumstances.

# Appendices

Appendix A – BU Life Planning

Structure and Functions

The Business Unit Life Plan comprises four key components that facilitate development, ensure alignment across functions, and integrate strategic inputs. These components, along with their respective ownership and storage locations, are detailed in the table below.

| Components/Scope | Frequency | Timing | Ownership | Accountability | Location |
| --- | --- | --- | --- | --- | --- |
| Strategy Development & Scenario Planning | Yearly - or as needed | Q4 | COO | Mgr Planning | Confidential Sharepoint (Advisor owned) |
| Long Term Growth Plan | Minimum Yearly | Q1 | COO | Asset Management, E&P Planning and BA | Confidential Drive (BD owned) |
| LTP (10+ years) | Yearly | Q3 | COO | Asset Management, E&P Planning and BA | Confidential Drive (Finance owned) |
| End of Life Strategy | Yearly | Varies by PSC | SVP | Asset Management | Confidential SharePoint (AM owned) |

- Strategy Development & Scenario Planning

This component serves as a Business Unit (BU)-level Collaborative and Decision Quality (CDQ) session, aimed at formulating long-term portfolio planning scenarios. The CDQ leverages corporate methodologies and aligns with the Corporate-BU strategy. Owned by the COO and supported by SVP for Portfolio Management, this component includes discussions on exit strategies, potential market influences, and key drivers. The strategy undergoes annual validation and review with the corporate team and is revisited as needed, particularly in response to significant political, market, or commercial events that may impact its outcome.

- Long Term Growth Plan

The COO is the owner of this component, with Asset Management responsible for collecting and supporting the development of the BU's long-term growth opportunities. The "BU Long-Term Growth Plan" extends beyond the LTP and is reviewed by the Leadership Team (LT) at least annually.

This plan includes action steps for developing identified opportunities and assesses their potential magnitude. It also incorporates strategies to optimize portfolio value. The associated documents are confidential and maintained by the Planning team.

- LTP beyond 10 years

This component is divided into two major areas: Development (Assets) and Exploration (New Ventures):

  - Development

Focuses on future fields and utilizes a systematic new-opportunities selection criteria. It includes economic valuations as part of the LTP process and manages Plans of Development (POD) within existing PSCs. This area is reviewed annually in preparation for the LTP process and is informed by inventory generation initiatives within the assets.

  - Exploration

Covers future fields, data acquisition, and entry into new PSCs. It applies a systematic new-opportunities selection criteria and conducts economic valuations within the LTP. Similar to Development, Exploration is reviewed annually in advance of the LTP process and is driven by inventory generation initiatives within the assets.

- End of Life Strategy

End-of-PSC-life management involves the development and execution of the Abandonment and Site Restoration (ASR) strategy. This includes comprehensive planning and oversight to ensure the effective and compliant closure of operations.

Appendix B – Meeting Term of Reference

Appendix C – Planning Activity Inclusion Criteria

|  |  |  |  |  | Mandatory |  |  |  | Discretionary |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Recommended |  |  |  | Not included |  |  |
|  |  | ACTIVITY | Activity Type | 7-day | 30-day | 90-Day | 24 Month |  | 10-Year |  | BU Life |
|  |  | Schedule Visualization Granularity |  | Daily | Daily | Daily | Monthly |  | Quarterly |  | Yearly |
| Integrated Activities (Common across functions) |  |  |  |  |  |  |  |  |  |  |  |
|  |  | All vendor / contractor work aside from core staffing | Function | ALL | ALL | > 20% total workforce | > 20% total workforce |  | > 20% total workforce |  |  |
|  |  | Shutdowns or rate reductions | Integrated |  | Lower ability to meet demand | Lower ability to meet demand | Lower ability to meet demand |  | > 10% of facility capacity |  |  |
|  |  | Additional logistics (boats, helicopter, vehicles) | Function | ALL | ALL | > 20% capacity | > 20% capacity |  | > 20% capacity |  |  |
|  |  | Emergency exercises | Integrated |  | Tier 1 and above, excluding table top | Tier 1 and above, excluding table top | Tier 1 and above, excluding table top |  |  |  |  |
|  |  | Project Milestones | Integrated |  | ALL | ALL | ALL |  | Major Project |  | Major Project |
|  |  | Major Procurement Milestones | Integrated |  | ALL | MEDCO E&P GRISSIK Approval, SKK Migas Approval | MEDCO E&P GRISSIK Approval, SKK Migas Approval, MEPI Approval |  | MEPI Approval |  | - |
|  |  | ACTIVITY | Activity Type | 7-day | 30-day | 90-Day | 24 Month |  | 10-Year |  | BU Life |
|  |  | Schedule Visualization Granularity |  | Daily | Daily | Daily | Monthly |  | Quarterly |  | Yearly |
|  |  | Additional external resources | Function | ALL | ALL | > 20% total workforce | > 20% total workforce |  | > 20% total workforce |  |  |
|  |  | Additional internal resources | Function | ALL | ALL | > 20% total workforce | > 20% total workforce |  | > 20% total workforce |  |  |
|  |  | Major HAZOP / HAZID requirements | Function | ALL | ALL | >10 FTE | >10 FTE |  |  |  |  |
|  |  | Supply vessel and other significant logistics schedules | Function | - | ALL | ALL | Inter Island |  |  |  |  |
|  |  | IAAN Follow up action | Integrated |  | Sig/Hi Risk, and/or production impact | Sig/Hi Risk, and/or production impact | Sig/Hi Risk, and/or production impact |  |  |  |  |
|  |  | SCE activities | Integrated |  | Major impairment – Hi/Sig Risk, and/or production impact | Major impairment – Hi/Sig Risk, and/or production impact | Major impairment – Hi/Sig Risk, and/or production impact |  |  |  |  |
|  |  | Major Contract expirations and milestone dates for re-tenders | Integrated |  | >5MM | >5MM | >5MM |  | >20MM |  |  |
|  |  | Hiring and Training Processes | Function | ALL | ALL | ALL | ALL |  | Critical Skills |  |  |
|  |  | Manpower Planning Process (RPTK, etc.) | Function | ALL | ALL | ALL | ALL |  |  |  |  |
|  |  | Marine Surveys | Integrated |  | ALL | ALL | >5 MM |  |  |  |  |
| Facilities Maintenance |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Major engine overhaul and change-outs | Integrated |  | ALL | ALL | ALL |  | >$ 5MM |  |  |
|  |  | Major equipment change-outs/repair | Integrated |  | ALL | ALL | ALL |  | >$ 1MM |  |  |
|  |  | Non Routine and Intelligent Pigging | Integrated |  | ALL | ALL | ALL |  | >$ 1MM |  |  |
|  |  | Major Asset Integrity Activities | Integrated |  | ALL | ALL | ALL |  | >$ 5MM |  |  |
|  |  | Major Maintenance Milestones | Integrated |  | ALL | ALL | ALL |  | >$ 5MM |  |  |
|  |  | Metering Certifications | Integrated |  | ALL | ALL | ALL |  | - |  |  |
|  |  | Equipment Certifications (License to operate) | Integrated |  | ALL | ALL | ALL |  | - |  |  |
| Project Delivery Corridor |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Major Approval (AFE, Tender or Award Plan, etc.) | Integrated |  | ALL | ALL | ALL |  | >$50MM |  | >$100MM |
|  |  | Project Milestones (Engineering, Procurement, Construction, Installation) | Integrated |  | ALL | ALL | ALL |  | >$75MM |  | >$100MM |
|  | Pre Development & Development |  |  |  |  |  |  |  |  |
|  | Development Screening, Development concept milestones |  | Integrated |  | ALL | ALL | ALL |  | >$10MM |  | >$100MM |
|  | Milestones |  | Integrated |  | ALL | ALL | ALL |  | >$75MM |  | >$100MM |
|  | New Well Drilling |  |  |  |  |  |  |  |  |  |  |
|  |  | Major Approval (AFE, Tender or Award Plan, etc.) | Integrated |  | ALL | ALL | >$10MM |  | >$20MM |  | >$20MM |
|  |  | Drilling & Completion Milestones (well pad, spud, completion, flow test) | Integrated |  | ALL | ALL | >$10MM |  | >$20MM |  | >$20MM |
| Well Services & Maintanance |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Major Approval (AFE, Tender or Award Plan, etc.) | Function | ALL | ALL | ALL | ALL |  | >$1MM |  | >$1MM |
|  |  | Well Service & Maintenance | Integrated |  | ALL | ALL | >$500K |  | >$5MM |  |  |
| Commercial |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Crude Liftings | Integrated |  | ALL | ALL | ALL |  |  |  |  |
|  |  | Gas Contract Maintenance Declaration | Integrated |  | ALL | ALL | ALL |  |  |  |  |
|  |  | Gas Contract Reserve Reporting and DMR | Integrated |  | ALL | ALL | ALL |  |  |  |  |
|  |  | Contract Negotiations | Function |  | ALL | ALL | ALL |  | ALL |  | ALL |
|  |  | Contract Milestones | Function | - | ALL | ALL | ALL |  | ALL |  | ALL |
|  |  | Contract Termination | Integrated |  | ALL | ALL | ALL |  | ALL |  | ALL |
|  |  | Reserve Certification | Integrated |  | ALL | ALL | ALL |  |  |  |  |
|  |  | Buyer Maintenance | Integrated |  | ALL | ALL | ALL |  |  |  |  |
|  |  | Demand Fluctuations | Integrated |  | ALL | ALL | >10% normal |  |  |  |  |
| General Stakeholder Engagement |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Major Approval (AFE, Tender or Award Plan, etc.) | Integrated | - | ALL | ALL | ALL |  | >$ 1 MM |  |  |
|  |  | VIP Visits | Function | - | ALL | ALL | ALL |  |  |  |  |
|  |  | Non-VIP Visits | Function | - | ALL | ALL |  |  |  |  |  |
|  |  | Global / Corporate Function visit | Function | - | ALL | ALL |  |  |  |  |  |
|  |  | Audits and reviews | Integrated | - | ALL | ALL | ALL |  | - |  |  |
| Government of Indonesia |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Work Program and Budget (WP&B) Process | Integrated |  | ALL | ALL | ALL |  |  |  |  |
|  |  | WP&B Revision and Monitoring Process | Integrated |  | ALL | ALL | ALL |  |  |  |  |
|  |  | Major Permitting | Integrated |  | ALL | ALL | ALL |  | ALL |  | ALL |
|  |  | PSC Expiration/Extension | Integrated |  | ALL | ALL | ALL |  | ALL |  | ALL |
| Community and Business Environment |  |  |  |  |  |  |  |  |  |  |  |
|  |  | CSR Campaigns | Function | - | ALL | ALL | ALL |  | ALL |  |  |
|  |  | Community Events (COP driven) | Function | ALL | ALL | ALL | ALL |  | ALL |  |  |
| Partners |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Technical Committee Meetings | Integrated |  | ALL | ALL | ALL |  |  |  |  |
|  |  | Operating Committee Meetings | Integrated |  | ALL | ALL | ALL |  |  |  |  |
| Internal |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Long Term Plan Process | Integrated |  | ALL | ALL | ALL |  | ALL |  |  |
|  |  | Cash and Earnings Process | Function | ALL | ALL | ALL | ALL |  |  |  |  |
|  |  | SMOG | Function | ALL | ALL | ALL | ALL |  |  |  |  |
|  |  | Reserve Booking | Function | ALL | ALL | ALL | ALL |  |  |  |  |
|  |  | Core Manpower Requirements | Function | ALL | ALL | ALL | ALL |  | ALL |  | ALL |
|  |  | Core Resource Requirements | Function | ALL | ALL | ALL | ALL |  | ALL |  | ALL |

Appendix D – Data Input Attribute

| No. | Data Attribute | Description | Operational | Tactical | Strategic |
| --- | --- | --- | --- | --- | --- |
| 1 | Medco E&P Grissik Ltd (MEPG) Department | Department name, eq Operations, Drilling, Project, Development, Logistic, etc. | Mandatory | Mandatory | Mandatory |
| 2 | Medco E&P Grissik Ltd (MEPG) Activity ID | String of combination, to be decided further | Mandatory | Mandatory | Mandatory |
| 3 | Medco E&P Grissik Ltd (MEPG) PMO ID | Unique Identification of order in BPM (Sequential number can be used when PMO # is not applicable) | Mandatory |  |  |
| 4 | Medco E&P Grissik Ltd (MEPG) Project ID |  | Mandatory |  |  |
| 5 | Contractor Internal Project ID |  | Mandatory |  |  |
| 6 | Routine/Non Routine |  | Mandatory |  |  |
| 7 | Location | Field locations | Mandatory | Mandatory |  |
| 8 | BPM Functional Location | Is the location where an activity is to be performed (where applicable, this should be made as specific as possible) | Mandatory |  |  |
| 9 | Plant System |  | Mandatory |  |  |
| 10 | Plant SubSystem |  | Mandatory |  |  |
| 11 | Hydrocarbon/Electrical/Utility |  | Mandatory |  |  |
| 12 | Main Work Center | Is the discipline responsible for the work (particularly when more than 1 disciplines involved) | Mandatory |  |  |
| 13 | Activity Name |  | Mandatory | Mandatory | Mandatory |
|  |  |  | Mandatory |  |  |
| 14 | Start | The plan date when an activity is to start in the field | Mandatory | Mandatory |  |
| 15 | Finish | The plan date when an activity is to finish in the field. | Mandatory | Mandatory |  |
| 16 | Duration | Duration is suggested to be in "day" if the duration of an activity is less than 1 day please use fraction e.g. 0.5 day etc. (1day = 12 hours). A work performed continuously for 24 hours can still be claimed as 1 day but please put note in the "additional information" column. | Mandatory |  |  |
| 17 | Actual Start |  |  |  |  |
| 18 | Actual Finish |  |  |  |  |
| 19 | Actual Duration (day) |  |  |  |  |
| 20 | Job Owner | The personnel responsible for the job from preparations until completion. |  |  |  |
| 21 | Work Leader | The personnel responsible for execution of the job in the field |  |  |  |
| 22 | Hotwork Needed | Yes/No question to confirm if the work is or is not a Hotwork. | Mandatory |  |  |
| 23 | MOC Needed | Yes/No question to confirm if the work is or is not require MOC. | Mandatory |  |  |
| 24 | Plant Shutdown Needed | Does the work require plant to shutdown | Mandatory | Mandatory | Mandatory |
| 25 | Impact LPO | Potential estimated LPO due to the work | Mandatory | Mandatory | Mandatory |
| 26 | Safety Barrier Needed | Safety critical isolation needed | Mandatory |  |  |
| 27 | Crane Need | Does it need crane, at what condition of the crane | Mandatory |  |  |
| 28 | Scaffolding Need | Does it need scaffolding | Mandatory |  |  |
| 29 | Other Need (specify) | This is to indicate special requirement for a work e.g. require shutdown, require a crane to do the work, etc. | Mandatory |  |  |
| 30 | POB Constraint |  | Mandatory | Mandatory | Mandatory |
| 31 | Material Status | The information of the materials required for the job: status (where?), weight (need crane?), Size (space required?) |  |  |  |
| 32 | WorkPack Status |  |  |  |  |
| 33 | Discipline - Field Crew | Field Crew is field-based employee required to dedicatedly support the job. |  |  |  |
| 34 | Number of Field Crew |  |  |  |  |
| 35 | Medco E&P Grissik Ltd (MEPG) non field Dept. | MEDCO E&P GRISSIK Non-field is non-field based MEDCO E&P GRISSIK employee(s) mobilized to perform a job in the field (including Supraco, Singgar). |  |  |  |
| 36 | Number of Medco E&P Grissik Ltd (MEPG) non-field |  |  |  |  |
| 37 | Third Party Company | 3rd Party is any government official and/ or 3rd Party employees that TEMPORARILY come to the field to execute or witness the work |  |  |  |
| 38 | Third Party Number |  |  |  |  |
| 39 | Total Number of People to execute | Number of manpower required to perform the job | Mandatory | Mandatory | Mandatory |
| 40 | Estimated Manhours | Planned number of direct manhours required to execute the job | Mandatory |  |  |
| 41 | Contractor Sched.Ready (Y/N) |  | Mandatory |  |  |
| 42 | Budgeted (Y/N?) |  | Mandatory | Mandatory | Mandatory |
| 43 | Estimated Cost |  | Mandatory | Mandatory | Mandatory |
| 44 | Budget Source |  | Mandatory |  |  |
| 45 | Potential Consequences | Use HSE 5x5 Consequences matrix | Mandatory | Mandatory | Mandatory |
| 46 | Likelihood | Use HSE 5x5 Likelihood matrix | Mandatory | Mandatory | Mandatory |
| 47 | Risk Ranks | Consequences x Likelihood | Mandatory | Mandatory | Mandatory |
| 48 | Primary LSR | Main LSR that migh involve the task | Mandatory |  |  |
| 49 | Priority | If not sure about "Priority", please leave it blank. The Schedule Review Meeting will determine which activity has higher priority over another. |  |  |  |
| 50 | Additional Info | Any important info that has not been included in the other column, or will further explain the contain of other columns. |  |  |  |

Appendix E – Prioritization Matrix for Operational Horizon

Appendix F – Activity Change Request Process

- Reason for Plan Change

Changes to the 30-day plan must be approved by the Plan Owner due to the potential risks associated with adding or modifying activities. Such changes, if not carefully managed, could lead to Health, Safety, and Environmental (HSE) incidents, failure to meet forecasted deadlines, or negative impacts on overall plan performance.

There are three types of change to the plan:

- Addition of New Activities

- Deletion of Existing Activities

- Modifications to Ongoing Activities within the 30-Day Plan

For operations activities, all proposed changes must be reviewed and approved during the daily or weekly meetings with the Superintendent, OIM, and/or Offsite Managers. These changes must also be documented through email confirmation or meeting minutes. Alignment with the existing schedule and required resources must be addressed during the meeting.

Any proposed changes that may impact constraints—such as safety, operational resources, logistics support, production, or budget—must be initiated through a Plan Change Request. At a minimum, such changes require approval from the Plan Owner.

- New Activity to Plan

This process ensures that all unplanned activities with potential impacts on constraints (such as accommodations, operational resources, logistics support), production, or budget are clearly defined and agreed upon before being incorporated into the ongoing 30-day plans.

Changes with potential impacts on constraints—such as safety, operational resources, logistics support, production, or budget—require an approved Plan Change Request (PCR) form, with the following process:

- Submission of PCR Form:

  - The Activity Sponsor completes and submits the PCR form to the Asset Planner for evaluation.

  - If there are no significant constraints (e.g., accommodations or SIMOPS issues), the changes can be forwarded directly to the Plan Owner for approval.

  - If there is a major impact on constraints, the matter must be escalated to the OIM for resolution. Depending on the complexity of the change, the OIM may convene a meeting with the Field Manager to discuss and resolve the issue.

- The Field Manager reviews the PCR form, considering the priority, justification, and potential impacts on the current plan. Based on this review, the Field Manager decides whether to approve or reject the proposed activity.

- The Asset Planner informs the Activity Sponsor whether the proposed activity is approved or rejected, including the reasons for the decision. If the change impacts other activities, the owners of those activities must be informed of the implications, and adjustments or reprioritization may be required.

- Deletion of Activities

The deletion of an activity can be decided by the OIM after evaluating the following factors:

- Impact on Budget and Production Opportunity: The potential consequences of continuing the activity versus its removal, including financial and production considerations.

- Resource Reallocation: The reallocation of resources freed by the deletion and how it affects other operations.

- Impact on Other Activities: Any effects on other activities that depend on or follow sequentially from the deleted activity.

Approval for deleting an activity that may impact constraints or resources must be documented through a PCR. The OIM is responsible for providing justification based on the considerations outlined above, while the Asset Planner is responsible for recording and documenting the justification.

- Changes within ongoing 30 day planning

Any change to a plan that extends beyond three days from its original 30-day schedule requires alignment with the existing schedule and available resources. If the change impacts other activities, the respective activity owners must be informed, as they may need to re-prioritize their work accordingly.

| To be filled by Plan Originator |  |  |
| --- | --- | --- |
| PCR No: | Asset Area: |  |
| Description of Original Plan | Description of Plan Change / New Addition |  |
| Justification for Plan Change / New Addition |  |  |
| Change on : Duration Dates Risk Resource Competency Describe : |  |  |
| Impact to : Safety Risk Production POB Budget/Costs Other Constraints/Logistics Tactical Planning Describe : |  |  |
| How the changes will be managed : |  |  |
| To be filled by Planner |  |  |
| List of Other Planned Activities being impacted |  |  |
| Approver Comment |  | Approver Signature / Date Name: |
| Planner Completion to Change Schedule and Resources Notify impacted activities |  | Planner Signature / Date Name: |

Appendix G – Conducting After Action Review

- Planning the AAR

- Identify the activity to be reviewed.

- Decide on the timing of the AAR – it should be conducted as soon as possible after the event.

- Coordinate with the leader to determine who needs to attend.

- Ensure a suitable location or room is available.

The leader should encourage the organization to capture key lessons in preparation for the AAR

- Preparing the AAR

- Select a facilitator.

- Confirm the date, time, location, and duration of the session in advance.

- Set expectations for attendees to come prepared and ready to focus on key issues

- Conducting the AAR

- The AAR should be focused, facilitated, and last no longer than 60 minutes.

- Typically, the AAR will involve input from multiple perspectives and will not be conducted in isolation.

- Promote active participation through group discussion.

- Facilitate discussions in chronological order of events.

- Record key lessons on a flip chart or similar tool.

- Clearly define and agree on action items, including the responsible parties, specific tasks, and deadlines.

- Highlight the potential impact of each lesson where known.

- Follow up the AAR

- Ensure documented lessons are tracked to closure, with their added value quantified. Use an Action Register to monitor progress.

- Provide the leader with access to the AAR for discussion during lessons learned meetings.

| What was planned | What happened & why | Impact it had | Lesson | Action Required |
| --- | --- | --- | --- | --- |

- Value of $ Save

- The objective is to capture cost savings and potential loss prevention achieved through planning activities, teamwork, and collaboration across functions.

- The purpose is to quantify the impact of planning and scheduling activities, as well as teamwork and interdepartmental collaboration. This aims to drive continuous improvement and motivate others to enhance their efforts in planning, teamwork, and collaboration